## Gantt Chart (hidden)
Cleaning Confirmed
Painting Confirmed
Tentative
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | END DATE | DURATION (Days) |  | PCT OF TASK COMPLETE | [5 empty] | 2024-06-01 | [19 empty] | 2024-07-01 | [23 empty] | 2024-08-01 | [19 empty] | 2024-09-01 | [19 empty] | 2024-10-01 | [19 empty] | 2024-11-01 | [19 empty] | 2025-01-01 | [24 empty] | 2025-02-01 | [19 empty] | 2025-03-01 | [19 empty] | 2025-04-01 | [19 empty] | 2025-05-01 | [19 empty] | 2025-06-01 | [14 empty] | 2025-07-01 | [19 empty] | 2025-08-01 | [14 empty] | 2025-09-01
[6 empty] | ACTUAL MATERIAL COST |  | WEEK 22 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24 |  |  |  |  | WEEK 25 |  |  |  |  | WEEK 26 |  |  |  |  | WEEK 27 |  |  |  |  | WEEK 28 |  |  |  |  | WEEK 29 |  |  |  |  | WEEK 30 |  |  |  |  | WEEK 31 |  |  |  |  | WEEK 31 | [6 empty] | WEEK 32 |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | T | W | R | F | F | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Blumberg Homes - 2323 Jefferson - Tester | Tester | 2024-06-24 | 2025-03-19 | 268 |  | #REF!
| Rough clean units 1,2,3,4 | David R | 2024-06-24 | 2024-06-25 | 2 | bar: WEEK 26 M to WEEK 26 T
| Final clean units 1,2 | David R | 2024-07-09 | 2024-07-09 | 1 | bar: WEEK 28 T
| Power wash units 1,2 | David R | 2024-07-09 | 2024-07-09 | 1 | bar: WEEK 28 T
| Final clean units 3,4 | David R | 2024-07-15 | 2024-07-15 | 1 | bar: WEEK 29 M
| Power wash units 3,4 | David R | 2024-07-15 | 2024-07-15 | 1 | bar: WEEK 29 M
| Touch up units 1,2 | Francy R | 2024-07-23 | 2024-07-23 | 1 | bar: WEEK 30 T
| Touch up units 3,4 Rough clean units 5,7 | Francy R | 2024-07-25 | 2024-07-25 | 1 | bar: WEEK 30 R
| Rough clean units 8,9 | Francy R | 2024-07-26 | 2024-07-26 | 1 | bar: WEEK 30 F
| Final claen units 5,7 | Francy R | 2024-07-30 | 2024-07-30 | 1 | bar: WEEK 30 F; WEEK 31 T
| Power washing units 5-9 | David R | 2024-07-31 | 2024-07-31 | 1 | bar: WEEK 30 F; WEEK 31 W
| Final clean units 8,9 | David R | 2024-08-02 | 2024-08-02 | 1 | bar: WEEK 31 F
| Rough clean units 6,10,11,12,13 Touch up unit 7 | Francy R | 2024-08-07 | 2024-08-09 | 3 | bar: WEEK 31 W to WEEK 32 F
| Final clean units 6, 10, 11, 12, 13 | Francy R | 2024-08-14 | 2024-08-16 | 3 | bar: WEEK 8 W to WEEK 8 F
| Power washing units 10 - 13 | Oscar G | 2024-08-21 | 2024-08-21 | 1 | bar: WEEK 9 M
| Touch up units 11,12,13 | David R | 2024-08-26 | 2024-08-26 | 1 | bar: WEEK 9 W
| Rough clean units 14,15 | David R | 2024-08-30 | 2024-08-30 | 1 | bar: WEEK 9 F
| Rough clean units 16,17 | David R | 2024-09-03 | 2024-09-03 | 1 | bar: WEEK 6 T
| Final clean units 14,15 | David R | 2024-09-17 | 2024-09-17 | 1 | bar: WEEK 8 T
| Rough clean units 18,19, 20, 22 Final clean units 16, 17, 20, 22 | Francy R | 2024-09-18 | 2024-09-20 | 3 | bar: WEEK 8 W to WEEK 8 F
| Power washing units 14 - 26 Rough clean units 21, 24, 25, 26,23, Final clean units 19,21,23,24,25,26 Touch up units 18,20,22,24 | David R Francy R | 2024-09-23 | 2024-09-27 | 5 | bar: WEEK 9 M to WEEK 9 F
| Touch up units 14,17,19,21,23,25,26 | Francy R | 2024-09-30 | 2024-10-01 | 2 | bar: WEEK 6 M to WEEK 6 T
| Rough clean units 29,30, Final clean units 29,30 | Francy R | 2024-11-27 | 2024-11-27 | 1 | bar: WEEK 9 W
| Rough clean units 27,28 Final clean units 27,28 | Francy R | 2024-11-29 | 2024-11-29 | 1 | bar: WEEK 9 F
| Touch up units 27,28,29 Powerwashing units 27 -36 | Francy R David R | 2024-12-10 | 2024-12-10 | 1 | bar: WEEK 9 F
| Rough clean units 31,33,34 Final clean units 31,33,33 Touch up unit 30 | David R | 2024-12-18 | 2024-12-18 | 1
| Touch up unit 22 | David R | 2024-12-23 | 2024-12-23 | 0.5
| Rough clean units 32, 35, 36 Final clean units 32, 35, 36 | David R | 2025-01-08 | 2025-01-08 | 1 | bar: WEEK 2 W
| Touch up unit 22, 23 | David R | 2025-01-14 | 2025-01-14 | 1 | bar: WEEK 3 T
| Touch up unit 36 | Martha R | 2025-02-20 | 2025-02-20 | 0.5
| Touch up units 27,36 | Martha R | 2025-03-19 | 2025-03-19 | 0.5
2 | Victorian Village - 440 South Road - Harkins | Harkins | 2025-01-13 | 2025-05-27 | 134 |  | 0%
2.1 | Rough Clean unit 174 | David R | 2025-01-13 | 2025-01-14 | 1 | bar: WEEK 5 M
2.2 | Rough Clean unit 169, 170, 171, 172, 173, 175, 176, 177, 178, 180, 181, 179 | Francy | 2025-01-30 | 2025-01-31 | 1.2448
2.3 | Rough Clean Unit 182, 183, 184, 185, 186, 187, 188, 189, 190, 191, 192, 193, 194, | Francy | 2025-02-17 | 2025-02-18 | 1.238
2.4 | Final Clean Unit 169, 170, 171, 172, 173, 174, 175, 176, 177, 178, 179, 181 | Francy | 2025-02-27 | 2025-02-28 | 1.2313
2.5 | Final Clean unit 182, 183, 184, 185, 186, 187, 188, 189, 190, 191, 194, | Francy | 2025-03-06 | 2025-03-07 | 1.2245
2.6 | Rugh Clean & Final clean units: 180, 192, 193, 195, 196, 197, 198, 199, 200, 201, 202, 203, 204, 205 | Francy | 2025-03-18 | 2025-03-21 | 1.2177
2.7 | Rugh Clean & Final clean units: 207, 208, 209, 210, 211, 212, 213, 214, 215, 216, 218, 219, 220 Rugh clean pasillos pisos 1,2,3,4 | Francy | 2025-03-31 | 2025-04-02 | 1.2109
2.8 | Rough & final clean back of house areas (floor 2,3,4) Rough clean stairs 1,2,3,4 | David R | 2025-04-07 | 2025-04-07 | 1.2041
2.9 | Final clean pasillos pisos 2,3,4 | David R | 2025-04-10 | 2025-04-10 | 1.1973
2.10 | Final clean stairs 1,2,3,4 Rough & final clean back of house areas (floor 1) Final clean pasillo piso 1 | Osacar G | 2025-04-15 | 2025-04-15 | 1.1905
2.11 | Touch up unidades piso 4, 3 (parcial) | Francy R | 2025-05-07 | 2025-05-09 | 1.1838
2.12 | Touch up unidades piso 3, 2, y 1, escaleras 1,2,3 y 4, pasillos piso 4-1, lobby, ventanas externas piso1, areas comunes | Francy R | 2025-05-12 | 2025-05-15 | 1.177
2.13 | Wax back of house areas | Osacar G | 2025-05-16 | 2025-05-16 | 1.1702
2.14 | powerwashing | David R | 2025-05-27 | 2025-05-27 | 1.1634
1.1566
1.1498
1.143
1.1363
3 | Harper Apartments - 307 Harper Dr - Ingerman | Ingerman | 2025-03-25 | 2025-06-26 | 93
3.1 | Rugh Clean & Final clean units: 105,120 | Francy | 2025-03-25 | 2025-03-25 | 1 |  | 0%
3.2 | Rugh Clean, 51 units | David | 2025-04-14 | 2025-04-18 | 5 |  | 0%
3.3 | Rugh Clean, 22 units | David | 2025-04-21 | 2025-04-22 | 2 |  | 0%
3.4 | Final Clean, 22 units | Oscar | 2025-05-06 | 2025-05-09 | 4 |  | 0%
| Final Clean, 41 units | Oscar | 2025-05-12 | 2025-05-16 | 5 |  | 0%
3.4 | Final Clean units & common areas | Francy | 2025-05-19 | 2025-05-22 | 4 |  | 0%
3.5 | Touch up, 61 units | David | 2025-06-16 | 2025-06-20 | 5
3.6 | Touch up, 15 units & common areas | David | 2025-06-23 | 2025-06-25 | 3
4 | Willows at Forest Drive - Forest Drive Annapolis - Ingerman | Ingerman | 2025-05-12 | 2025-05-12
4.1 | Rugh Clean, Building 1 | David | 2025-05-12 | 2025-05-14 | 3 |  | 0%
4.2 | Rugh Clean Building 2 Section A & B | David | 2025-06-02 | 2025-06-03 | 2 |  | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
7 | 20-30 W Allens - 20 West Allens Lane - TCG Tester | Tester | 2025-09-03
11 | Birchwood 1150 Norton Av LIMPIEZA | Ingerman | POR DEFINIR
| Limpieza techo, unidades y areas comunes | David R | 2025-07-28 | 2025-07-29 | 2 |  | 0%
| Limpieza pisos 2 y 3 | David R | 2025-07-30 | 2025-07-30 | 1
| Limpieza piso 1 | Oscar | 2025-08-15 | 2025-08-15 | 1
| Limpieza Piso 1 y 2 | OScar | 2025-09-09 | 2025-09-10 | 2
| Rough Clean unidades piso 1 | Bastian | 2015-10-14 | 2015-10-14 | 1
10 | Birchwood 1150 Norton Av PINTURA | Ingerman | 2025-07-24
| Preparacion, cubrir, encintar unidades, desmontar puertas | David R | 2025-07-24 | 2025-07-25 | 2 |  | 0%
| Primeado unidades pso 1 | David R | 2025-07-26 | 2025-07-29 | 3 |  | 0%
| Instalacion puertas | David R | 2025-07-31 | 2025-07-31 | 1
| Caulking & putty unidades piso 1. | David R | 2025-08-12 | 2025-08-13 | 2
| Primeado unidades piso 2 y 3 | David R | 2025-09-02 | 2025-09-15 | 12
| Preparacion, cubrir, encintar pasillo | David R | 2025-09-09 | 2025-09-09 | 1
| Primeado Areas comunes, lobby, Pasillos piso 1 , 2, 3 y escaleras #1 y #2 | David R | 2025-09-10 | 2025-09-14 | 5
| Caulking & putty unidades piso 1. Primer puertas Piso 3 | David R | 2025-09-15 | 2025-09-19 | 5
| Pintura unidades 101, 102, 103, 104 (Paredes y techo) | David R | 2025-09-23 | 2025-09-23 | 1
| Pintura unidades 105, 106, 108, 109, 110, 111, 114 (Paredes y techo) | David R | 2025-09-24 | 2025-09-24 | 1
| Pintura Trim unidades piso 1 | David R | 2025-09-25 | 2025-09-26 | 2
| Caulking & putty trim areas comunes piso 1 | David R | 2025-09-29 | 2025-09-29 | 1
| Limpieza y caulkin ventanas piso 1 | David R | 2025-09-30 | 2025-10-01 | 2
| Primer puertas metalicas | David R | 2025-10-02 | 2025-10-03 | 2
| Pintura areas comunes | David R | 2025-10-06 | 2025-10-09 | 4
| Pintura puertas principales y frame unidades y puesrtas areas comunes y servicio | David R | 2025-10-10 | 2025-10-14 | 3
| Pintura unidades piso 2 | David R | 2025-10-15 | 2025-10-17 | ?
10 | Saddle Brook -BLOCK 1401, LOT 18 - | Ingerman | 2025-11-01
4.1 | Project Objectives | Steve L |  |  | 0 |  | 0%
4.2 | Quality Deliverables | Allen W |  |  | 0 |  | 0%
4.3 | Effort and Cost Tracking | Malik M |  |  | 0 |  | 0%

## Gantt Chart 2026
SUEEP
| PROJECT TITLE |  | Gantt Chart Projects |  |  |  |  | COMPANY NAME | [6 empty] | SUEEP
| PROJECT MANAGER |  | David Rodriguez |  |  |  |  | START DATE | [6 empty] | 2025-10-16
| WBS NUMBER | TASK TITLE | PROJECT MANAGER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | 2025-10-01 | [19 empty] | 2025-11-01 | [19 empty] | 2025-12-01 | [19 empty] | 2026-01-01 | [24 empty] | 2026-02-01 | [19 empty] | 2026-03-01 | [19 empty] | 2026-04-01
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
| 1 | 20 W ALLENS LANE TCG Tester Construction Group
Rough Clean
| 1.1 | Floor 4 | David Rodriguez | 2025-10-16 | 2025-10-17 | 2 | 100% | bar: WEEK 3 R to WEEK 3 F; WEEK 2 M; WEEK 2 W to WEEK 2 R
| 1.1 | Floor 3 | Bastian Sepulveda | 2025-10-23 | 2025-10-24 | 2 | 100% | bar: WEEK 4 R to WEEK 4 F; WEEK 2 M; WEEK 2 W to WEEK 2 R
|  | Floor 2 | Bastian Sepulveda | 2025-11-03 | 2025-11-04 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T; WEEK 2 M; WEEK 2 W to WEEK 2 R
| 1.3 | Floor 1 | David Rodriguez | 2025-12-15 | 2025-12-15 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
| 2 | Final Clean
| 2.1 | Floor 3 | David Rodriguez | 2025-12-16 | 2025-12-17 | 2 | 100% | bar: WEEK 2 M to WEEK 2 R
| 2.2 | Floor 2 | David Rodriguez | 2025-12-17 | 2025-12-18 | 2 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
| 2.3 | Lobby | David Rodriguez | 2025-12-18 | 2025-12-18 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
|  | Floor 4 | David Rodriguez | 2026-01-12 | 2026-01-13 | 2 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 3 M to WEEK 3 T
| 2.4 | Floor 1 | David Rodriguez | 2026-01-29 | 2026-01-29 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 5 R
| 3 | Touch Up
| 3.1 | Floor 2 | David Rodriguez | 2026-01-16 | 2026-01-16 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 3 F
| 3.2 | Floor 3 | David Rodriguez | 2026-01-21 | 2026-01-22 | 2 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 4 W to WEEK 4 R
| 3.2.1 | Floor 4 | David Rodriguez | 2026-02-11 | 2026-02-12 | 2 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 7 W to WEEK 7 R
| 3.2.2 | Floor 1 | David Rodriguez | 2026-02-19 | 2026-02-19 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 8 R
| 3.3 | Common Areas | David Rodriguez | 2026-02-20 | 2026-02-20 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 8 F
Christ Home Cottages - Harkins Builders
Rough Clean
|  | Units 590 / 592 | David Rodriguez | 2025-12-08 | 2025-12-08 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
|  | Units 580 / 582 | David Rodriguez | 2025-12-11 | 2025-12-11 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
|  | Units 570 / 572 | David Rodriguez | 2025-12-19 | 2025-12-19 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 3 F
| 2 | Final Clean
|  | Units 590 / 592 | David Rodriguez | 2026-02-10 | 2026-02-10 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 7 T
|  | Units 580 / 582 . | David Rodriguez | 2026-03-04 | 2026-03-04 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 10 W
|  | Units 570 / 572 | David Rodriguez | 2026-03-11 | 2026-03-11 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 11 W
| 3 | Touch Up
|  | Units 590 / 592 | David Rodriguez | 2026-03-30 | 2026-03-30 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 13 M
|  | Units 580 / 582 . | David Rodriguez | 2026-03-30 | 2026-03-30 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 13 M
|  | Units 570 / 572 | David Rodriguez | 2026-03-30 | 2026-03-30 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 13 M
Change Order
|  | Power-washing units 570, 572, 580, 582, 590, 592 | David Rodriguez | 2026-04-06 | 2026-04-06 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 2 M
Saddle Brook - Ingerman
Rough Clean
0% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
0% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
0% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
Final Clean
0% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
0% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
0% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
Touch Up
0% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
0% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
0% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R
Change Order
|  | Exterior clean & rough clean 1.5 building | David Rodriguez | 2025-12-22 | 2025-12-22 | 1 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 4 M
|  | Exterior clean & rough clean of the 3 buildings | David Rodriguez | 2026-03-16 | 2026-03-17 | 2 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 12 M to WEEK 12 T
|  | Clean windows, tubs & showers building1 clean windows building 2 & 3 | David Rodriguez | 2026-04-13 | 2026-04-14 | 2 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R; WEEK 3 M to WEEK 3 T
20 W ALLENS LANE TCG Tester Construction Group
Rough Clean
|  | Floor 4 | David Rodriguez | 2025-10-16 | 2025-10-17 | 2 | 100% | bar: WEEK 2 M; WEEK 2 W to WEEK 2 R

## Project Tracking Commercial
PROJECT DETAILS | [11 empty] | COST/HOURS |  |  |  |  | Invoicing
DATE | JOB TITLE | NAME | HOURS | RATE/HR | Supervisor | DESCRIPTION | % DONE | MANPOWER | CONTRACT VALUE | ESTIMATED MATERIAL COST | ESTIMATED TRAVEL EXPENSE | ESTIMATED LABOR COST | ACTUAL LABOR COST | ACTUAL MATERIAL COST | ESTIMATED HOURS | ACTUAL HOURS | % Invoiced | Invoice Status
Blumberg Homes - 2323 Jefferson - Tester |  |  |  |  | David Rodriguez | Final Cleaning | 100% |  |  | 849.6 |  | 19760 | 17020 |  | 512 | 952
2024-06-24 | Supervisor | David Rodriguez | 8 | 27.5 | David Rodriguez | Rough clean units 1,2 | [6 empty] | 220 |  |  | 8
2024-06-24 | Cleaner | Francy Rincon | 8 | 15 | David Rodriguez | Rough clean units 1,2 | [6 empty] | 120 |  |  | 8
2024-06-24 | Cleaner | Arlett Flores | 8 | 15 | David Rodriguez | Rough clean units 1,2 | [6 empty] | 120 |  |  | 8
2024-06-24 | Supervisor | David Rodriguez | 8 | 27.5 | David Rodriguez | Rough clean units 3,4 | [6 empty] | 220 |  |  | 8
2024-06-25 | Cleaner | Arlett Flores | 8 | 15 | David Rodriguez | Rough clean units 3,4 | [6 empty] | 120 |  |  | 8
2024-06-25 | Cleaner | Fernanda | 8 | 15 | David Rodriguez | Rough clean units 3,4 | [6 empty] | 120 |  |  | 8
2024-07-09 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | Final Cleaning units 1,2 | [6 empty] | 180 |  |  | 8
2024-07-09 | Cleaner | Adriana | 8 | 15 | Francy Rincon | Final Cleaning units 1,2 | [6 empty] | 120 |  |  | 8
2024-07-09 | Supervisor powerwashing | Oscar Giraldo | 8 | 22.5 | Oscar Giraldo | Powerwashing units 1,2 | [6 empty] | 180 |  |  | 8
2024-07-09 | Powerwashing | Juan Pablo Torres | 8 | 15 | Oscar Giraldo | Powerwashing units 1,2 | [6 empty] | 120 |  |  | 8
2024-07-15 | Supervisor | Martha Rios | 8 | 22.5 | Martha Rios | Final Cleaning units 3,4 | [6 empty] | 180 |  |  | 8
2024-07-15 | Cleaner | Arlett Flores | 8 | 15 | Martha Rios | Final Cleaning units 3,4 | [6 empty] | 120 |  |  | 8
2024-07-15 | Cleaner | Yolanda | 8 | 15 | Martha Rios | Final Cleaning units 3,4 | [6 empty] | 120 |  |  | 8
2024-07-15 | Supervisor powerwashing | Oscar Giraldo | 8 | 22.5 | Oscar Giraldo | Powerwashing units 3,4 | [6 empty] | 180 |  |  | 8
2024-07-15 | Powerwashing | Julian | 8 | 15 | Oscar Giraldo | Powerwashing units 3,4 | [6 empty] | 120 |  |  | 8
2024-07-23 | Supervisor/Cleaning | Francy Rincon | 8 | 22.5 | Francy Rincon | Touch up units 1,2 | [6 empty] | 180 |  |  | 8
2024-07-25 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | Touch up units 3,4 Rough clean units 5,7 | [6 empty] | 180 |  |  | 8
2024-07-25 | Cleaner | Magda | 8 | 15 | Francy Rincon | Touch up units 3,4 | [6 empty] | 120 |  |  | 8
2024-07-25 | Cleaner | Grazi | 8 | 15 | Francy Rincon | Rough clean units 5,7 | [6 empty] | 120 |  |  | 8
2024-07-25 | Cleaner | Paula | 8 | 15 | Francy Rincon | Rough clean units 5,7 | [6 empty] | 120 |  |  | 8
2024-07-26 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | Rough clean units 8, 9 | [6 empty] | 180 |  |  | 8
2024-07-26 | Cleaner | Adriana | 8 | 15 | Francy Rincon | Rough clean units 8, 9 | [6 empty] | 120 |  |  | 8
2024-07-26 | Cleaner | Grazi | 8 | 15 | Francy Rincon | Rough clean units 8, 9 | [6 empty] | 120 |  |  | 8
2024-07-30 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | Final clean units 5,7 | [6 empty] | 180 |  |  | 8
2024-07-30 | Cleaner | Adriana | 8 | 15 | Francy Rincon | Final clean units 5,7 | [6 empty] | 120 |  |  | 8
2024-07-30 | Cleaner | Leidy | 8 | 15 | Francy Rincon | Final clean units 5,7 | [6 empty] | 120 |  |  | 8
2024-07-31 | Supervisor powerwashing | David Rodriguez | 8 | 27.5 | David Rodriguez | Powerwashing units 5 -9 | [6 empty] | 220 |  |  | 8
2024-07-31 | Powerwashing | Oscar Giraldo | 8 | 15 | David Rodriguez | Powerwashing units 5 -9 | [6 empty] | 120 |  |  | 8
2024-08-02 | Supervisor | David Rodriguez | 8 | 27.5 | David Rodriguez | Final clean units 8,9 | [6 empty] | 220 |  |  | 8
2024-08-02 | Cleaner | Francy Rincon | 8 | 15 | David Rodriguez | Final clean units 8,9 | [6 empty] | 120 |  |  | 8
2024-08-02 | Cleaner | Adriana | 8 | 15 | David Rodriguez | Final clean units 8,9 | [6 empty] | 120 |  |  | 8
2024-08-07 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | Touch up unit 7 Rough clean unit 6, 10 | [6 empty] | 180 |  |  | 8
2024-08-07 | Cleaner | Adriana | 8 | 15 | Francy Rincon | Touch up unit 7 Rough clean unit 6, 10 | [6 empty] | 120 |  |  | 8
2024-08-07 | Cleaner | Catalina | 8 | 15 | Francy Rincon | Touch up unit 7 Rough clean unit 6, 10 | [6 empty] | 120 |  |  | 8
2024-08-08 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | Rough clean units 11, 12 | [6 empty] | 180 |  |  | 8
2024-08-08 | Cleaner | Adriana | 8 | 15 | Francy Rincon | Rough clean units 11, 12 | [6 empty] | 120 |  |  | 8
2024-08-08 | Cleaner | Catalina | 8 | 15 | Francy Rincon | Rough clean units 11, 12 | [6 empty] | 120 |  |  | 8
2024-08-09 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | Rough clean unit 13 | [6 empty] | 180 |  |  | 8
2024-08-09 | Cleaner | Adriana | 8 | 15 | Francy Rincon | Rough clean unit 13 | [6 empty] | 120 |  |  | 8
2024-08-14 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | Final clean units 6, 10 | [6 empty] | 180 |  |  | 8
2024-08-14 | Cleaner | Adriana | 8 | 15 | Francy Rincon | Final clean units 6, 10 | [6 empty] | 120 |  |  | 8
2024-08-14 | Cleaner | Ana B | 8 | 15 | Francy Rincon | Final clean units 6, 10 | [6 empty] | 120 |  |  | 8
2024-08-15 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | Final clean units 12, 13 | [6 empty] | 180 |  |  | 8
2024-08-15 | Cleaner | Mayra | 8 | 15 | Francy Rincon | Final clean units 12, 13 | [6 empty] | 120 |  |  | 8
2024-08-15 | Cleaner | Liseth | 8 | 15 | Francy Rincon | Final clean units 12, 13 | [6 empty] | 120 |  |  | 8
2024-08-16 | Supervisor/Cleaning | Francy Rincon | 8 | 22.5 | Francy Rincon | Final clean unit 11 | [6 empty] | 180 |  |  | 8
2024-08-21 | Supervisor powerwashing | Oscar Giraldo | 8 | 22.5 | Oscar Giraldo | Powerwashing units 10 - 13 | [6 empty] | 180 |  |  | 8
2024-08-21 | Powerwashing | William | 8 | 15 | Oscar Giraldo | Powerwashing units 10 - 13 | [6 empty] | 120 |  |  | 8
2024-08-26 | Supervisor | David Rodriguez | 8 | 27.5 | David Rodriguez | Touch up units 11 - 13 | [6 empty] | 220 |  |  | 8
2024-08-26 | Cleaner | Liseth | 8 | 15 | David Rodriguez | Touch up units 11 - 13 | [6 empty] | 120 |  |  | 8
2024-08-26 | Cleaner | Mayra | 8 | 15 | David Rodriguez | Touch up units 11 - 13 | [6 empty] | 120 |  |  | 8
2024-08-30 | Supervisor | David Rodriguez | 8 | 27.5 | David Rodriguez | Rough clean units 14, 15 | [6 empty] | 220 |  |  | 8
2024-08-30 | Cleaner | Mayra | 8 | 15 | David Rodriguez | Rough clean units 14, 15 | [6 empty] | 120 |  |  | 8
2024-08-30 | Cleaner | Liseth | 8 | 15 | David Rodriguez | Rough clean units 14, 15 | [6 empty] | 120 |  |  | 8
2024-09-03 | Supervisor | David Rodriguez | 8 | 27.5 | David Rodriguez | Rough clean units 16, 17 | [6 empty] | 220 |  |  | 8
2024-09-03 | Cleaner | Francy Rincon | 8 | 15 | David Rodriguez | Rough clean units 14, 15 | [6 empty] | 120 |  |  | 8
2024-09-03 | Cleaner | Liseth | 8 | 15 | David Rodriguez | Rough clean units 14, 15 | [6 empty] | 120 |  |  | 8
2024-09-17 | Supervisor | David Rodriguez | 8 | 27.5 | David Rodriguez | Final clean units 14, 15 | [6 empty] | 220 |  |  | 8
2024-09-17 | Cleaner | Francy Rincon | 8 | 22.5 | David Rodriguez | Final clean units 14, 15 | [6 empty] | 180 |  |  | 8
2024-09-17 | Cleaner | Liseth | 8 | 15 | David Rodriguez | Final clean units 14, 15 | [6 empty] | 120 |  |  | 8
2024-09-18 | Cleaner | Liseth | 8 | 22.5 | David Rodriguez | Final clean units 18 & 19 | [6 empty] | 180 |  |  | 8
2024-09-18 | Cleaner | Mayra | 8 | 15 | David Rodriguez | Final clean units 18 & 19 | [6 empty] | 120 |  |  | 8
2024-09-18 | Supervisor | Francy Rincon | 8 | 22.5 | David Rodriguez | Final clean units 18 & 19 | [6 empty] | 180 |  |  | 8
2024-09-19 | Supervisor | Francy Rincon | 8 | 22.5 | David Rodriguez | Final Clean unit 16 Rough & Final Clean Unit 20 | [6 empty] | 180 |  |  | 8
2024-09-19 | Cleaner | Liseth | 8 | 15 | David Rodriguez | Final Clean unit 16 Rough & Final Clean Unit 20 | [6 empty] | 120 |  |  | 8
2024-09-20 | Supervisor | Francy Rincon | 8 | 22.5 | David Rodriguez | Final Clean unit 17 Rough & Final Clean Unit 22 | [6 empty] | 180 |  |  | 8
2024-09-20 | Cleaner | Liseth | 8 | 15 | David Rodriguez | Final Clean unit 17 Rough & Final Clean Unit 22 | [6 empty] | 120 |  |  | 8
2024-09-20 | Cleaner | Grazi | 8 | 15 | David Rodriguez | Final Clean unit 17 Rough & Final Clean Unit 22 | [6 empty] | 120 |  |  | 8
2024-09-23 | Supervisor | David Rodriguez | 8 | 27.5 | David Rodriguez | Powerwashing units 14 - 26 | [6 empty] | 220 |  |  | 8
2024-09-23 | Cleaner | Oscar Giraldo | 8 | 15 | David Rodriguez | Powerwashing units 14 - 26 | [6 empty] | 120 |  |  | 8
2024-09-23 | Supervisor | Francy Rincon | 8 | 22.5 | David Rodriguez | Rough & Final Clean Units 21 & 24 (quedo pendiente piso 1) | [6 empty] | 180 |  |  | 8
2024-09-23 | Cleaner | Leidy | 8 | 15 | David Rodriguez | Rough & Final Clean Units 21 & 24 (quedo pendiente piso 1) | [6 empty] | 120 |  |  | 8
2024-09-23 | Cleaner | Grazi | 8 | 15 | David Rodriguez | Rough & Final Clean Units 21 & 24 | [6 empty] | 120 |  |  | 8
2024-09-24 | Cleaner | Viviana | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-09-24 | Supervisor | Francy Rincon | 8 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 8
2024-09-24 | Cleaner | Grazi | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-09-25 | Supervisor | David Rodriguez | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
2024-09-25 | Cleaner | Liseth | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-09-25 | Cleaner | Grazi | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-09-25 | Cleaner | Viviana | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-09-26 | Supervisor | Francy Rincon | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-09-26 | Cleaner | Viviana | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-09-26 | Cleaner | Liseth | 8 | 15 | David Rodriguez | [7 empty] | 120
2024-09-27 | Supervisor | Francy Rincon | 8 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 8
2024-09-27 | Cleaner | Liseth | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-09-27 | Cleaner | Grazi | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-09-30 | Supervisor | Francy Rincon | 8 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 8
2024-09-30 | Cleaner | Liseth | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-09-30 | Cleaner | Grazi | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-10-01 | Supervisor | Francy Rincon | 8 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 8
2024-10-01 | Cleaner | Liseth | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-10-01 | Cleaner | Grazi | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-11-27 | Supervisor | Francy Rincon | 8 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 8
2024-11-27 | Cleaner | Viviana | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-11-27 | Cleaner | Adriele | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-11-27 | Cleaner | Daivisanes | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-11-29 | Supervisor | Francy Rincon | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-11-29 | Cleaner | Daivisanes | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-11-29 | Cleaner | Jaqueline | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-11-29 | Cleaner | Ingrid | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-12-10 | Supervisor | Francy Rincon | 8 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 8
2024-12-10 | Cleaner | Jaqueline | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-12-10 | Cleaner | Daivisanes | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-12-10 | Supervisor | David Rodriguez | 8 | 22.5 | David Rodriguez | Power wash | [6 empty] | 180 |  |  | 8
2024-12-10 | Cleaner | Fabian | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-12-18 | Supervisor | David Rodriguez | 8 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 8
2024-12-18 | Cleaner | Daivisanes | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-12-18 | Cleaner | Jaqueline | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-12-18 | Cleaner | Viviana | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-12-19 | Supervisor | David Rodriguez | 8 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 8
2024-12-19 | Cleaner | Jaqueline | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-12-19 | Cleaner | Daivisanes | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2024-12-23 | Supervisor | David Rodriguez | 8 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 8
2025-01-08 | Supervisor | David Rodriguez | 8 | 15 | David Rodriguez | Rough & Final clean unit 32, 35, 36 | [6 empty] | 120 |  |  | 8
2025-01-08 | Cleaner | Juliani | 8 | 15 | David Rodriguez | Rough & Final clean unit 32, 35, 36 | [6 empty] | 120 |  |  | 8
2025-01-08 | Cleaner | Sandra | 8 | 15 | David Rodriguez | Rough & Final clean unit 32, 35, 36 | [6 empty] | 120 |  |  | 8
2025-01-08 | Cleaner | Cecilia | 8 | 15 | David Rodriguez | Rough & Final clean unit 32, 35, 36 | [6 empty] | 120 |  |  | 8
2025-01-14 | Cleaner | Juliani | 8 | 15 | David Rodriguez | Touch up unit 22 & 33 | [6 empty] | 120 |  |  | 8
2025-01-14 | Cleaner | Sandra | 8 | 15 | David Rodriguez | Touch up unit 22 & 33 | [6 empty] | 120 |  |  | 8
2025-02-20 | Supervisor | Martha Rios | 4 | 27.5 | David Rodriguez | [7 empty] | 110 |  |  | 4
2025-02-20 | Cleaner | (Cleaner) | 4 | 15 | Martha Rios | [7 empty] | 60 |  |  | 4
2025-03-19 | Supervisor | Martha Rios | 4 | 22.5 | Martha Rios | [7 empty] | 90
2025-03-19 | Cleaner | (Cleaner) | 4 | 15 | Martha Rios | [7 empty] | 60
Victorian Village - 440 South Road - Harkins |  |  |  |  | David Rodriguez | Final Cleaning | 100% |  |  | 383.4 |  | 28860 | 14575 |  | 808 | 832
2025-01-13 | Supervisor | David Rodriguez | 6 | 27.5 | David Rodriguez | [7 empty] | 165 |  |  | 6
2025-01-13 | Cleaner | Juliani | 6 | 15 | David Rodriguez | [7 empty] | 90 |  |  | 6
2025-01-13 | Cleaner | Sandra | 6 | 15 | David Rodriguez | [7 empty] | 90 |  |  | 6
2025-01-30 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-01-30 | Cleaner | Viviana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-01-30 | Cleaner | Diana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-01-30 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-01-31 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-01-31 | Cleaner | Viviana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-01-31 | Cleaner | Diana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-01-31 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-17 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-02-17 | Cleaner | Viviana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-17 | Cleaner | Diana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-17 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-18 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-02-18 | Cleaner | Viviana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-18 | Cleaner | Diana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-18 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-27 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-02-27 | Cleaner | Viviana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-27 | Cleaner | Diana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-27 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-28 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-02-28 | Cleaner | Viviana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-28 | Cleaner | Diana | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-02-28 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-06 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-03-06 | Cleaner | Juliani | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-06 | Cleaner |  | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-06 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-07 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-03-07 | Cleaner | Juliani | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-07 | Cleaner | Grazy | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-07 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-18 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-03-18 | Cleaner | Juliani | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-18 | Cleaner | Milner | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-18 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-19 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-03-19 | Cleaner | Juliani | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-19 | Cleaner | Milner | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-19 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-19 | Cleaner | Jhon Fonseca | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-20 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-03-20 | Cleaner | Juliani | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-20 | Cleaner | Milner | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-20 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-20 | Cleaner | Jhon Fonseca | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-21 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-03-21 | Cleaner | Juliani | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-21 | Cleaner | Milner | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-21 | Cleaner | Divianes | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-31 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-03-31 | Cleaner | Davisane | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-31 | Cleaner | Milner | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-31 | Cleaner | Malbira | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-31 | Cleaner | Jhon Fonseca | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-01 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-04-01 | Cleaner | Davisane | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-01 | Cleaner | Milner | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-01 | Cleaner | Yiselle | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-01 | Cleaner | Jhon Fonseca | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-02 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-04-02 | Cleaner | Davisane | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-02 | Cleaner | Juliani | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-02 | Cleaner | Yiselle | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-02 | Cleaner | Jhon Fonseca | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-07 | Supervisor | David Rodriguez | 10 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
2025-04-07 | Cleaner | Davisane | 10 | 15 | David Rodriguez | [7 empty] | 150 |  |  | 8
2025-04-07 | Cleaner | Juliani | 10 | 15 | David Rodriguez | [7 empty] | 150 |  |  | 8
2025-04-07 | Cleaner | Malbira | 10 | 15 | David Rodriguez | [7 empty] | 150 |  |  | 8
2025-04-10 | Supervisor | David Rodriguez | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
2025-04-10 | Cleaner | Davisane | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-10 | Cleaner | Juliani | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-10 | Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-15 | Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
2025-04-15 | Cleaner | Davisane | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-04-15 | Cleaner | Yiselle | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-07 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-05-07 | Cleaner | Wanda | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-07 | Cleaner | Geline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-08 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-05-08 | Cleaner | Wanda | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-08 | Cleaner | Geline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-09 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-05-09 | Cleaner | Geline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-12 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-05-12 | Cleaner | Wanda | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-12 | Cleaner | Alex | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-12 | Cleaner | Gerline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-13 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-05-13 | Cleaner | Gerline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-13 | Cleaner | Jaqueline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-13 | Cleaner | Alex | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-14 | Supervisor | Francy Rincon | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-05-14 | Cleaner | Gerline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-14 | Cleaner | Wanda | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-15 | Supervisor | David Rodriguez | 11 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 11
2025-05-15 | Cleaner | Francy | 11 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 11
2025-05-16 | Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
2025-05-16 | Wax | Nelson | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
2025-05-27 | powerwashing | David Rodriguez | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
2025-05-27 | powerwashing | Francy | 8 | 22.5 | David Rodriguez | [7 empty] | 180 |  |  | 8
Harper Apartments - 307 Harper Drive - Ingerman |  |  |  |  | David Rodriguez | Final Cleaning | 100% |  |  | 383.4 |  | 33820 | 18301.25 |  | 808 | 1012.5
2025-03-25 | Supervisor | Francy | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-03-25 | Cleaner | Juliani | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-03-25 | Cleaner | Davisane | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-14 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
2025-04-14 | Cleaner | Juliani | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-14 | Cleaner | Davisane | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-14 | Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-15 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
2025-04-15 | Cleaner | Juliani | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-15 | Cleaner | Francy | 8 | 15 | David Rodriguez |  | 0% | [5 empty] | 120 |  |  | 8
2025-04-15 | Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-16 | Supervisor | Francy R | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-04-16 | Cleaner | Juliani | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-16 | Cleaner | Davisane | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-16 | Cleaner | Malbira | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-17 | Supervisor | Francy R | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-04-17 | Cleaner | Juliani | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-17 | Cleaner | Davisane | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-17 | Cleaner | Malbira | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-04-18 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
2025-04-18 | Cleaner | Juliani | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-18 | Cleaner | Francy | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-18 | Cleaner | Davisane | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2027-04-21 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
2027-04-21 | Cleaner | Juliani | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2027-04-21 | Cleaner | Francy | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2027-04-21 | Cleaner | Davisane | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-22 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
2025-04-22 | Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-22 | Cleaner | Alex | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-04-22 | Cleaner | Davisane | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-05-06 | Supervisor | Francy R | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-05-06 | Cleaner | Deivis | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-06 | Cleaner | Andrea | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-07 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
2025-05-07 | Cleaner | Oscar | 8 | 25 | David Rodriguez | [7 empty] | 200 |  |  | 8
2025-05-07 | Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-05-07 | Cleaner | Deivis | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-05-07 | Cleaner | Andrea | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-05-08 | Supervisor | Oscar G | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
2025-05-08 | Cleaner | Malbira | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-08 | Cleaner | Deivis | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-08 | Cleaner | Andrea | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-09 | Supervisor | Oscar G | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
2025-05-09 | Cleaner | Deivis | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-09 | Cleaner | Andrea | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-12 | Supervisor | Oscar G | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
2025-05-12 | Cleaner | Malbira | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-12 | Cleaner | Deivis | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-12 | Cleaner | Andrea | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-13 | Supervisor | Oscar G | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
2025-05-13 | Cleaner | Malbira | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-13 | Cleaner | Deivis | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-13 | Cleaner | Andrea | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-14 | Supervisor | Oscar G | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
2025-05-14 | Cleaner | Andrea | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-14 | Cleaner | Malbira | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-15 | Supervisor | Oscar G | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
2025-05-15 | Cleaner | Malbira | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-15 | Cleaner | Deivis | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-15 | Cleaner | Andrea | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-16 | Supervisor | Francy R | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
2025-05-16 | Cleaner | Malbira | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-16 | Cleaner | Deivis | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-16 | Cleaner | Andrea | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-16 | Cleaner | Gerline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-19 | Supervisor | Francy R | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
| Cleaner | Malbira | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
| Cleaner | Deivis | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
| Cleaner | Andrea | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
| Cleaner | Gerline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-20 | Supervisor | Francy R | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
| Cleaner | Malbira | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
| Cleaner | Deivis | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
| Cleaner | Andrea | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
| Cleaner | Gerline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-05-21 | Supervisor | Oscar G | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
| Cleaner | Malbira | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
| Cleaner | Deivis | 8 | 15 | Oscar Giraldo | [7 empty] | 120 |  |  | 8
2025-05-22 | Supervisor | Francy R | 8 | 22.5 | Francy Rincon | [7 empty] | 180 |  |  | 8
| Cleaner | Deivis | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
| Cleaner | Andrea | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
| Cleaner | Gerline | 8 | 15 | Francy Rincon | [7 empty] | 120 |  |  | 8
2025-06-16 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
| Cleaner | Deivis | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Gerline | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Oscar | 8 | 25 | David Rodriguez | [7 empty] | 200 |  |  | 8
| Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-06-17 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
| Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Deivis | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Andrea | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Oscar | 8 | 25 | David Rodriguez | [7 empty] | 200 |  |  | 8
2025-06-18 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
| Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Deivis | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Andrea | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Oscar | 8 | 25 | David Rodriguez | [7 empty] | 200 |  |  | 8
| Cleaner | Gerline | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-06-19 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
| Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Deivis | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Andrea | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Gerline | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-06-20 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
| Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Andrea | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Gerline | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Oscar | 8 | 25 | David Rodriguez | [7 empty] | 200 |  |  | 8
2025-06-23 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
| Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Francisca | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Andrea | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Dora | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Oscar | 8 | 25 | David Rodriguez | [7 empty] | 200 |  |  | 8
2025-06-24 | Supervisor | David R | 8 | 27.5 | David Rodriguez | [7 empty] | 220 |  |  | 8
| Cleaner | Malbira | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Francisca | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Andrea | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Dora | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Oscar | 8 | 25 | David Rodriguez | [7 empty] | 200 |  |  | 8
| Cleaner | Deivis | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
| Cleaner | Gisele | 8 | 15 | David Rodriguez | [7 empty] | 120 |  |  | 8
2025-06-25 | Supervisor | David R | 9.5 | 27.5 | David Rodriguez | [7 empty] | 261.25 |  |  | 9.5
| Cleaner | Oscar | 9.5 | 25 | David Rodriguez | [7 empty] | 237.5 |  |  | 9.5
| Cleaner | Deivis | 9.5 | 15 | David Rodriguez | [7 empty] | 142.5 |  |  | 9.5
Willows at Forrest Drive - Annapolis Maryland - Ingerman |  |  |  |  | David Rodriguez | Final Cleaning | 100% |  |  | 310 |  | 23160 | 14846.86 | 3340.74 | 320 | 527.5
2025-05-12 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Rough Clean Building 1 | [6 empty] | 220 | 292.52 | Hotel | 8
| Cleaner | Juan | 8 | 15 | David Rodriguez | Rough Clean Building 1 | [6 empty] | 120 |  |  | 8
| Cleaner | Tulio | 8 | 15 | David Rodriguez | Rough Clean Building 1 | [6 empty] | 120 |  |  | 8
2025-05-13 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Rough Clean Building 1 | [6 empty] | 220 |  |  | 8
| Cleaner | Juan | 8 | 15 | David Rodriguez | Rough Clean Building 1 | [6 empty] | 120 |  |  | 8
| Cleaner | Tulio | 8 | 15 | David Rodriguez | Rough Clean Building 1 |  |  |  | 27 |  |  | 120 |  |  | 8
2025-05-14 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Rough Clean Building 1 | [6 empty] | 220 |  |  | 8
| Cleaner | Juan | 8 | 15 | David Rodriguez | Rough Clean Building 1 | [6 empty] | 120 |  |  | 8
| Cleaner | Tulio | 8 | 15 | David Rodriguez | Rough Clean Building 1 | [6 empty] | 120 |  |  | 8
2025-06-02 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Rough Clean Building 2 | [6 empty] | 220 | 150 | Hotel | 8
| Supervisor | Oscar | 8 | 25 | David Rodriguez | Rough Clean Building 2 | [6 empty] | 200 |  |  | 8
| Cleaner | Juan | 8 | 15 | David Rodriguez | Rough Clean Building 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Tulio | 8 | 15 | David Rodriguez | Rough Clean Building 2 | [6 empty] | 120 |  |  | 8
2025-06-03 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Rough Clean Building 2 | [6 empty] | 220 |  |  | 8
| Supervisor | Oscar | 8 | 25 | David Rodriguez | Rough Clean Building 2 | [6 empty] | 200 |  |  | 8
| Cleaner | Juan | 8 | 15 | David Rodriguez | Rough Clean Building 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Tulio | 8 | 15 | David Rodriguez | Rough Clean Building 2 | [6 empty] | 120 |  |  | 8
2025-09-16 | PM | David Rodriguez | 8.5 | 31.25 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 250 | 96.03 | Supplies | 8.5
| Cleaner | Diana Diaz | 8.5 | 15 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 127.5 | 301.06 | Hotel | 8.5
| Cleaner | Elian David | 8.5 | 15 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 127.5 |  |  | 8.5
| Cleaner | Juan Benjumea | 8.5 | 15 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 127.5 |  |  | 8.5
2025-09-17 | PM | David Rodriguez | 9.5 | 31.25 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 250 |  |  | 9.5
| Cleaner | Diana Diaz | 9.5 | 15 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 142.5 |  |  | 9.5
| Cleaner | Elian David | 9.5 | 15 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 142.5 |  |  | 9.5
| Cleaner | Juan Benjumea | 9 | 15 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 135 |  |  | 9
2025-09-18 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 250 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean Building 1 | [6 empty] | 120 |  |  | 8
| Cleaner | Elian David | 8 | 15 | David Rodriguez | Final Clean Building 1 | [6 empty] | 120 |  |  | 8
| Cleaner | Juan Benjumea | 8 | 15 | David Rodriguez | Final Clean Building 1 | [6 empty] | 120 |  |  | 8
2025-09-25 | PM | David Rodriguez | 9 | 31.25 | David Rodriguez | Final Clean Building 1 | [6 empty] | 250 | 16.4 | Supplies | 9
| Supervisor | Bastian Sepulveda | 9 | 20 | David Rodriguez | Final Clean Building 1 | [6 empty] | 160 |  |  | 9
| Cleaner | Diana Diaz | 9 | 15 | David Rodriguez | Final Clean Building 1 | [6 empty] | 135 |  |  | 9
| Cleaner | Elian David | 9 | 15 | David Rodriguez | Final Clean Building 1 | [6 empty] | 135 |  |  | 9
| Cleaner | Juan Benjumea | 8 | 15 | David Rodriguez | Final Clean Building 1 | [6 empty] | 120 |  |  | 8
2025-10-13 | PM | David Rodriguez | 9 | 31.25 | David Rodriguez | Final Clean Building 2 | [6 empty] | 250 | 371.54 | Hotel | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 120 | 103.84 | Supplies | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 120 | 46.25 | Diesel | 8
| Cleaner | Carla Sepulveda | 8 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Juan Benjumea | 8 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 120 |  |  | 8
2025-10-14 | PM | David Rodriguez | 10 | 31.25 | David Rodriguez | Final Clean Building 2 | [6 empty] | 250 |  |  | 10
| Cleaner | Diana Diaz | 10 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 150 |  |  | 10
| Cleaner | Camila Cardenas | 10 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 150 |  |  | 10
| Cleaner | Carla Sepulveda | 10 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 150 |  |  | 10
| Cleaner | Juan Benjumea | 8 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 120 |  |  | 8
2025-10-15 | PM | David Rodriguez | 9 | 31.25 | David Rodriguez | Final Clean Building 2 | [6 empty] | 250 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Carla Sepulveda | 8 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Juan Benjumea | 8 | 15 | David Rodriguez | Final Clean Building 2 | [6 empty] | 120 |  |  | 8
2025-10-27 | PM | David Rodriguez | 9 | 28.84 | David Rodriguez | Final Clean Building 3 | [6 empty] | 230.72 | 454.82 | Hotel | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean Building 3 | [6 empty] | 120 | 34.22 | Diesel | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean Building 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Final Clean Building 3 | [6 empty] | 150 |  |  | 8
2025-10-28 | PM | David Rodriguez | 9 | 28.84 | David Rodriguez | Final Clean Building 3 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean Building 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean Building 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Final Clean Building 3 | [6 empty] | 150 |  |  | 8
2025-10-29 | PM | David Rodriguez | 9 | 28.84 | David Rodriguez | Final Clean Building 3 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean Building 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean Building 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Final Clean Building 3 | [6 empty] | 150 |  |  | 8
2025-10-30 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean Building 3 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 4 | 15 | David Rodriguez | Final Clean Building 3 | [6 empty] | 60 |  |  | 4
| Cleaner | Camila Cardenas | 4 | 15 | David Rodriguez | Final Clean Building 3 | [6 empty] | 60 |  |  | 4
| Cleaner | Elian Bonilla | 4 | 18.75 | David Rodriguez | Final Clean Building 3 | [6 empty] | 75 |  |  | 4
2025-11-05 | PM | David Rodriguez | 9 | 28.84 | David Rodriguez | Touch up Building 1 | [6 empty] | 230.72 | 346 | Hotel | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Touch up Building 1 | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Touch up Building 1 | [6 empty] | 120 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Touch up Building 1 | [6 empty] | 150 |  |  | 8
2025-11-06 | PM | David Rodriguez | 9 | 28.84 | David Rodriguez | Touch up Building 1 & 2 Sec A | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Touch up Building 1 & 2 Sec A | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Touch up Building 1 & 2 Sec A | [6 empty] | 120 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Touch up Building 1 & 2 Sec A | [6 empty] | 150 |  |  | 8
2025-11-07 | PM | David Rodriguez | 9 | 28.84 | David Rodriguez | Touch up Building 2 Sec A | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Touch up Building 2 Sec A | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Touch up Building 2 Sec A | [6 empty] | 120 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Touch up Building 2 Sec A | [6 empty] | 150 |  |  | 8
2025-11-08 | PM | David Rodriguez | 9 | 28.84 | David Rodriguez | Touch up Building 2 Sec B | [6 empty] | 230.72 | 319.01 | Hotel | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Touch up Building 2 Sec B | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Touch up Building 2 Sec B | [6 empty] | 120 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Touch up Building 2 Sec B | [6 empty] | 150 |  |  | 8
2025-11-19 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 230.72 | 767.39
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 120
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 120
2025-11-20 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 230.72
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 120
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 120
2025-11-21 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 230.72
| Cleaner | Diana Diaz | 4 | 15 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 60
| Cleaner | Camila Cardenas | 4 | 15 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 60
2025-11-22 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 230.72
| Cleaner | Diana Diaz | 4 | 15 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 60
| Cleaner | Camila Cardenas | 4 | 15 | David Rodriguez | Touch up Building 3 Sec A | [6 empty] | 60
2025-12-10 | PM | David Rodriguez | 8.5 | 28.84 | David Rodriguez | Touch up Building 3 Sec B | [6 empty] | 230.72 | 41.66 | Diesel
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Touch up Building 3 Sec B | [6 empty] | 120
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Touch up Building 3 Sec B | [6 empty] | 120
| Cleaner | Elian Bonilla | 8.5 | 18.75 | David Rodriguez | Touch up Building 3 Sec B | [6 empty] | 150
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Touch up Building 3 Sec B | [6 empty] | 120
Birchwood Lighthouse - 1150 Norton Ave - Ingerman |  |  |  |  | David Rodriguez | Painting | 100% |  |  | 25000 |  | 45000 | 74950.76 | 27176.37 | 2240 | 3152
2025-07-24 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Preparation before paintig | [6 empty] | 220 | 164.9 | 102127.13 | 8
2025-07-24 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Preparation before paintig | [6 empty] | 200 |  |  | 8
2025-07-24 | Pintor | Cesar Rico | 8 | 18.75 | David Rodriguez | Preparation before paintig | [6 empty] | 150 |  |  | 8
2025-07-24 | Auxiliar | Brahian Zamora | 8 | 15 | David Rodriguez | Preparation before paintig | [6 empty] | 120 |  |  | 8
2025-07-25 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Preparation before paintig | [6 empty] | 200 | 74.16 |  | 8
2025-07-25 | Pintor | Cesar Rico | 8 | 18.75 | David Rodriguez | Preparation before paintig | [6 empty] | 150 |  |  | 8
2025-07-25 | Pintor | Sandra Celis | 8 | 18.75 | David Rodriguez | Preparation before paintig | [6 empty] | 150 | 363.15 |  | 8
2025-07-25 | Auxiliar | Brahian Zamora | 8 | 15 | David Rodriguez | Preparation before paintig | [6 empty] | 120 |  |  | 8
2025-07-26 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer units 1st fl | [6 empty] | 200 | 712.85 |  | 8
2025-07-26 | Pintor | Cesar Rico | 8 | 25 | David Rodriguez | Primer units 1st fl | [6 empty] | 200 |  |  | 8
2025-07-26 | Pintor | Sandra Celis | 8 | 18.75 | David Rodriguez | Primer units 1st fl | [6 empty] | 150 |  |  | 8
2025-07-26 | Auxiliar | Brahian Zamora | 8 | 15 | David Rodriguez | Primer units 1st fl | [6 empty] | 120 |  |  | 8
2025-07-27 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer units 1st fl | [6 empty] | 200 | 570.28 |  | 8
2025-07-27 | Pintor | Cesar Rico | 8 | 25 | David Rodriguez | Primer units 1st fl | [6 empty] | 200 |  |  | 8
2025-07-27 | Pintor | Sandra Celis | 8 | 18.75 | David Rodriguez | Primer units 1st fl | [6 empty] | 150 |  |  | 8
2025-07-29 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Primer units 1st fl | [6 empty] | 220 | 213.86 |  | 8
2025-07-29 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer units 1st fl | [6 empty] | 200 | 163.12 |  | 8
2025-07-29 | Pintor | Cesar Rico | 8 | 25 | David Rodriguez | Primer units 1st fl | [6 empty] | 200 | 71.78 |  | 8
2025-07-29 | Pintor | Sandra Celis | 8 | 18.75 | David Rodriguez | Primer units 1st fl | [6 empty] | 150 |  |  | 8
2025-07-29 | Auxiliar | Alex Chino | 8 | 15 | David Rodriguez | Primer units 1st fl | [6 empty] | 120 |  |  | 8
2025-07-31 | PM; | David Rodriguez | 8 | 27.5 | David Rodriguez | Install doors | [6 empty] | 220 |  |  | 8
2025-07-31 | Auxiliar | Sebastian Hidalgo | 8 | 15 | David Rodriguez | Install doors | [6 empty] | 120 |  |  | 8
2025-08-12 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Caulking & putty trim units 1st fl | [6 empty] | 220 | 104.31 |  | 8
2025-08-12 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Caulking & putty trim units 1st fl | [6 empty] | 200 |  |  | 8
2025-08-13 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Caulking & putty trim units 1st fl | [6 empty] | 220 |  |  | 8
2025-08-13 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Caulking & putty trim units 1st fl | [6 empty] | 200 |  |  | 8
2025-09-02 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer units 2nd and 3rd fl | [6 empty] | 200 | 356.43 |  | 8
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-03 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer units 2nd and 3rd fl | [6 empty] | 200 | 1425.7 |  | 8
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-04 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Primer units 2nd and 3rd fl | [6 empty] | 220 | 285.14 |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer units 2nd and 3rd fl | [6 empty] | 200 |  |  | 8
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-05 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Primer units 2nd and 3rd fl | [6 empty] | 220 | 1425.7 |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer units 2nd and 3rd fl | [6 empty] | 200 |  |  | 8
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-06 | PM | David Rodriguez | 4 | 27.5 | David Rodriguez | Primer units 2nd and 3rd fl | [6 empty] | 110 |  |  | 4
| Superintendente | Oscar Giraldo | 4 | 25 | Oscar Giraldo | Primer units 2nd and 3rd fl | [6 empty] | 100 |  |  | 4
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-08 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Primer units 2nd and 3rd fl | [6 empty] | 220 | 1140.56 |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer units 2nd and 3rd fl | [6 empty] | 200 |  |  | 8
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-09 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Preparation before paintig corridors | [6 empty] | 200 |  |  | 8
| Preparador | Cesar Rico | 8 | 18.75 | David Rodriguez | Preparation before paintig corridors | [6 empty] | 150 |  |  | 8
| Preparador | Sandra Celis | 8 | 15 | David Rodriguez | Preparation before paintig corridors | [6 empty] | 120 |  |  | 8
| Contratista | Andres Loaiza | 8 |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-10 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Primer corridors 1st fl | [6 empty] | 220 | 1448.3 |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer corridors 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Cesar Rico | 4.5 | 25 | David Rodriguez | Primer corridors 1st fl | [6 empty] | 112.5 |  |  | 8
| Pintor | Sandra Celis | 4.5 | 18.75 | David Rodriguez | Primer corridors 1st fl | [6 empty] | 84.5 |  |  | 8
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-11 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Primer common areas 1st fl & lobby | [6 empty] | 220 | 147.26 |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer common areas 1st fl & lobby | [6 empty] | 200 | 74.18 |  | 8
| Pintor | Cesar Rico | 8 | 25 | David Rodriguez | Primer common areas 1st fl & lobby | [6 empty] | 200 |  |  | 8
| Pintor | Sandra Celis | 8 | 18.75 | David Rodriguez | Primer common areas 1st fl & lobby | [6 empty] | 150 |  |  | 8
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-12 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Primer corridors 2nd fl | [6 empty] | 220 | 121.31 |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer corridors 2nd fl | [6 empty] | 200 | 1069.28 |  | 8
| Pintor | Cesar Rico | 8 | 25 | David Rodriguez | Primer corridors 2nd fl | [6 empty] | 200 |  |  | 8
| Pintor | Sandra Celis | 8 | 18.75 | David Rodriguez | Primer corridors 2nd fl | [6 empty] | 150 |  |  | 8
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-13 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Primer corridors 3rd fl | [6 empty] | 220 |  |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer corridors 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Cesar Rico | 8 | 25 | David Rodriguez | Primer corridors 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Sandra Celis | 8 | 18.75 | David Rodriguez | Primer corridors 3rd fl | [6 empty] | 150 |  |  | 8
| Ayudante | Elian David | 8 | 15 | David Rodriguez | Primer corridors 3rd fl | [6 empty] | 120 |  |  | 8
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl
2025-09-14 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer stairs #1 y #2 | [6 empty] | 200 |  |  | 8
| Pintor | Cesar Rico | 8 | 25 | Oscar Giraldo | Primer stairs #1 y #2 | [6 empty] | 200 |  |  | 8
| Pintor | Sandra Celis | 8 | 18.75 | Oscar Giraldo | Primer stairs #1 y #2 | [6 empty] | 150 |  |  | 8
2025-09-15 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Caulking & putty trim units 1st fl | [6 empty] | 250 | 78.4 |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Caulking & putty trim units 1st fl | [6 empty] | 200 | 285.14 |  | 8
| Ayudante | Elian David | 8 | 15 | David Rodriguez | Caulking & putty trim units 1st fl | [6 empty] | 120 |  |  | 8
| Ayudante | Frank Coy | 8 | 15 | David Rodriguez | Caulking & putty trim units 1st fl | [6 empty] | 120 |  |  | 8
| Contratista | Andres Loaiza |  |  | David Rodriguez | Primer units 2nd and 3rd fl | [6 empty] | 6600
2025-09-16 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Caulking & putty trim units 1st fl | [6 empty] | 200 |  |  | 8
| Ayudante | Sebastian Hidalgo | 8 | 15 | Oscar Giraldo | Caulking & putty trim units 1st fl | [6 empty] | 120 |  |  | 8
| Ayudante | Frank Coy | 8 | 15 | Oscar Giraldo | Caulking & putty trim units 1st fl | [6 empty] | 120 |  |  | 8
2025-09-17 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer doors 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Oscar Giraldo | Primer doors 3rd fl | [6 empty] | 180 |  |  | 8
2025-09-18 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer doors 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Oscar Giraldo | Primer doors 3rd fl | [6 empty] | 180 |  |  | 8
2025-09-19 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Primer doors 3rd fl | [6 empty] | 250 |  |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer doors 3rd fl | [6 empty] | 200 |  |  | 8
| Ayudante | Frank Coy | 8 | 15 | Oscar Giraldo | Primer doors 3rd fl | [6 empty] | 120 |  |  | 8
2025-09-22 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Purchase material | [6 empty] | 250 | 1258.41 |  | 8
2025-09-23 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Painting units 1st fl | [6 empty] | 250 |  |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Oscar Giraldo | Painting units 1st fl | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 15 | David Rodriguez | Painting units 1st fl | [6 empty] | 120 |  |  | 8
| Pintor | Cesar Rico | 8 | 25 | Oscar Giraldo | Painting units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Sandra Celis | 8 | 22.5 | Oscar Giraldo | Painting units 1st fl | [6 empty] | 180 |  |  | 8
2025-09-24 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Painting units 1st fl | [6 empty] | 250 | 765.32 |  | 8
| Superintendente | Oscar Giraldo | 4 | 25 | Oscar Giraldo | Painting units 1st fl | [6 empty] | 100 | 765.32 |  | 8
| Pintor | Frank Coy | 8 | 22.5 | David Rodriguez | Painting units 1st fl | [6 empty] | 180 | 41.85 |  | 8
| Ayudante | Elian David | 8 | 15 | David Rodriguez | Painting units 1st fl | [6 empty] | 120 |  |  | 8
| Pintor | Cesar Rico | 8 | 25 | David Rodriguez | Painting units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Sandra Celis | 8 | 22.5 | David Rodriguez | Painting units 1st fl | [6 empty] | 180 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Painting units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Papa Fernando | 8 | 25 | David Rodriguez | Painting units 1st fl | [6 empty] | 200 |  |  | 8
2025-09-25 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting trim units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 180 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Papa Fernando | 8 | 25 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 200 |  |  | 8
| Supervisor | Bastian Sepulveda | 8 | 20 | Oscar Giraldo | Painting trim units 1st fl | [6 empty] | 160 |  |  | 8
2025-09-26 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 250 | 348.53 |  | 8
| Superintendente | Oscar Giraldo | 4 | 25 | Oscar Giraldo | Painting trim units 1st fl | [6 empty] | 100 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 180 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Papa Fernando | 8 | 25 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 200 |  |  | 8
| Ayudante | Elian David | 8 | 15 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 120 |  |  | 8
| Supervisor | Bastian Sepulveda | 8 | 20 | Oscar Giraldo | Painting trim units 1st fl | [6 empty] | 160 |  |  | 8
2025-09-29 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Caulking & putty trim common area 1st fl | [6 empty] | 250 |  |  | 8
| Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Caulking & putty trim common area 1st fl | [6 empty] | 200 |  |  | 8
| Supervisor | Bastian Sepulveda | 8 | 20 | Oscar Giraldo | Caulking & putty trim common area 1st fl | [6 empty] | 160 |  |  | 8
2025-09-30 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Windows cleaning & caulking 1st fl | [6 empty] | 200 |  |  | 8
| Ayudante | Elian David | 8 | 15 | Oscar Giraldo | Windows cleaning & caulking 1st fl | [6 empty] | 120 |  |  | 8
| Supervisor | Bastian Sepulveda | 8 | 20 | Oscar Giraldo | Windows cleaning & caulking 1st fl | [6 empty] | 160 |  |  | 8
2025-10-01 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Windows cleaning & caulking 1st fl | [6 empty] | 200 | 272.43 |  | 8
| Ayudante | Elian David | 8 | 15 | David Rodriguez | Windows cleaning & caulking 1st fl | [6 empty] | 120 | 14.85 |  | 8
| Supervisor | Bastian Sepulveda | 8 | 20 | Oscar Giraldo | Windows cleaning & caulking 1st fl | [6 empty] | 160 |  |  | 8
2025-10-02 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer Metal Doors | [6 empty] | 200 |  |  | 8
| Ayudante | Elian David | 8 | 15 | David Rodriguez | Primer Metal Doors | [6 empty] | 120 |  |  | 8
| Supervisor | Bastian Sepulveda | 8 | 20 | Oscar Giraldo | Primer Metal Doors | [6 empty] | 160 |  |  | 8
2025-10-03 | Superintendente | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Primer Metal Doors | [6 empty] | 200 | 531.57 |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Primer Metal Doors | [6 empty] | 180 | 51.37 |  | 8
| Supervisor | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Primer Metal Doors | [6 empty] | 160 |  |  | 8
2025-10-06 | Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting Common Areas | [6 empty] | 200 | 88.66 |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 160 | 59.11 |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 15 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 120 |  |  | 8
2025-10-07 | Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting Common Areas | [6 empty] | 200 |  |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 160 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 15 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 120 |  |  | 8
| Pintor | Jonathan Izaguirre | 8 | 18.75 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 150 |  |  | 8
2025-10-08 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Painting Common Areas | [6 empty] | 250 | 29.55 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting Common Areas | [6 empty] | 200 | 186.5 |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 160 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 15 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 120 |  |  | 8
| Pintor | Johnathan Izaguirre | 8 | 18.75 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 150 |  |  | 8
2025-10-09 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Painting Common Areas | [6 empty] | 250 |  |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting Common Areas | [6 empty] | 200 |  |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 160 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 15 | Bastian Sepulveda | Painting Common Areas | [6 empty] | 120 |  |  | 8
2025-10-10 | PM | David Rodriguez | 8 | 31.25 | David Rodriguez | Painting doors & frame common areas | [6 empty] | 250 | 10.58 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting doors & frame common areas | [6 empty] | 200 | 139.41 |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting doors & frame common areas | [6 empty] | 160 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Painting doors & frame common areas | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 15 | Bastian Sepulveda | Painting doors & frame common areas | [6 empty] | 120 |  |  | 8
2025-10-13 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting doors & frame common areas | [6 empty] | 160 | 236.42 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting doors & frame common areas | [6 empty] | 200 | 137.16 |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Painting doors & frame common areas | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 15 | Bastian Sepulveda | Painting doors & frame common areas | [6 empty] | 120 |  |  | 8
2025-10-14 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting doors & frame common areas | [6 empty] | 160 | 295.25 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting doors & frame common areas | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Painting doors & frame common areas | [6 empty] | 180 |  |  | 8
2025-10-15 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 160 | 459.2 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Pinting Units Floor 2 | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 15 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 120 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.74 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 150 |  |  | 8
| Ayudante | Carlos Giraldo | 8 | 15 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 120 |  |  | 8
2025-10-16 | Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Pinting Units Floor 2 | [6 empty] | 200 |  |  | 8
| PM | David Rodriguez | 4 | 28.84 | David Rodriguez | Pinting Units Floor 2 | [6 empty] | 115.36 | 845.39 |  | 4
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 180 | 39.2 |  | 8
| Ayudante | Elian David | 8 | 15 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 120 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.74 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 150 |  |  | 8
| Ayudante | Carlos Giraldo | 8 | 15 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 120 |  |  | 8
2025-10-17 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Pinting Units Floor 2 | [6 empty] | 230.72 |  |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Pinting Units Floor 2 | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 15 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 120 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.74 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 150 |  |  | 8
| Ayudante | Carlos Giraldo | 8 | 15 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 120 |  |  | 8
2025-10-20 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Pinting Units Floor 2 | [6 empty] | 230.72 | 1372.28 |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 160 | 252.32 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Pinting Units Floor 2 | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 18.75 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 150 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.74 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 150 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Painting trim units 1st fl | [6 empty] | 200 |  |  | 8
2025-10-21 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Pinting Units Floor 2 | [6 empty] | 230.72 | 174.26 |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Pinting Units Floor 2 | [6 empty] | 160 |  |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Pinting Units Floor 2 | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 18.75 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Pinting Units Floor 2 | [6 empty] | 200 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Pinting Units Floor 2 | [6 empty] | 200 |  |  | 8
2025-10-22 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 230.72 | 52.96 |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 160 | 174.26 |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 180 |  |  | 8
| Ayudante | Elian David | 8 | 18.75 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.74 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
2025-10-23 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 230.72 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.74 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
2025-10-24 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 230.72 |  |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Touchup units 1st fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 22.5 | Bastian Sepulveda | Touchup units 1st fl | [6 empty] | 180 |  |  | 8
| Ayudante | Elian Bonilla | 8 | 18.75 | Bastian Sepulveda | Touchup units 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.74 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Touchup units 1st fl | [6 empty] | 200 |  |  | 8
2025-10-27 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 160 |  |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.74 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150
2025-10-28 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 160 | 939.58 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting trim units 2nd fl | [6 empty] | 200 | 300.82 |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 180 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Touchup units 1st fl | [6 empty] | 200 |  |  | 8
2025-10-29 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 160 |  |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 180 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Touchup units 1st fl | [6 empty] | 200 |  |  | 8
2025-10-30 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 160 | 147.76 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Bastian Sepulveda | Painting trim units 2nd fl | [6 empty] | 180 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Touchup units 1st fl | [6 empty] | 200 |  |  | 8
2025-10-31 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 230.72 | 155.14 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting trim units 2nd fl | [6 empty] | 200 | 30.02 |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 150 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 180 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Painting trim units 2nd fl | [6 empty] | 200 |  |  | 8
| Ayudante | Elian Bonilla | 8 | 18.75 | David Rodriguez | Touchup units 1st fl | [6 empty] | 150 |  |  | 8
2025-11-03 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting units 3rd fl | [6 empty] | 230.72 | 627.29 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting units 3rd fl | [6 empty] | 200 | 9.06 |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 180 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting units 3rd fl | [6 empty] | 200 |  |  | 8
| Ayudante | Elian Bonilla | 8 | 18.75 | David Rodriguez | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
2025-11-04 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting units 3rd fl | [6 empty] | 230.72 | 913.08 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting units 3rd fl | [6 empty] | 200 | 121.84 |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 180 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting units 3rd fl | [6 empty] | 200 |  |  | 8
| Ayudante | Elian Bonilla | 8 | 18.75 | David Rodriguez | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
2025-11-05 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 160 | 88.66 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting units 3rd fl | [6 empty] | 200 | 174.26 |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
| Pintor | Fernando Coy | 8 | 25 | David Rodriguez | Painting units 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | David Rodriguez | Painting units 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
2025-11-06 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 160 | 760.02 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting units 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
2025-11-07 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 160 |  |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting units 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
2025-11-08 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 160 | 480.39 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting units 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 150 |  |  | 8
2025-11-09 | PM | David Rodriguez | 3 | 28.84 | David Rodriguez | Painting corridors 1st & 2nd Fl | [6 empty] | 86.52 | 334.54 |  | 3
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting corridors 1st & 2nd Fl | [6 empty] | 200 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Oscar Giraldo | Painting corridors 1st & 2nd Fl | [6 empty] | 150 |  |  | 8
| Pintor | Marvin Coy | 8 | 25 | Oscar Giraldo | Painting corridors 1st & 2nd Fl | [6 empty] | 200 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Oscar Giraldo | Painting corridors 1st & 2nd Fl | [6 empty] | 150 |  |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | Oscar Giraldo | Painting corridors 1st & 2nd Fl | [6 empty] | 150 |  |  | 8
2025-11-10 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 230.72 | 424.35 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting common areas 1st fl | [6 empty] | 160 | 156.8 |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Caulking | Alejandra Ramirez | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
| Caulking | Fabian Ruiz | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
| Caulking | Daniel Paucar | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
2025-11-11 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 230.72 | 174.26 |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting units 3rd fl | [6 empty] | 160 | 137.16 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting common areas 1st fl | [6 empty] | 160 | 82.98 |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 | 84.63 |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Oscar Giraldo | Painting corridors 1st & 2nd Fl | [6 empty] | 150 |  |  | 8
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Daniel Paucar | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Caulking | Alejandra Ramirez | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
| Caulking | Fabian Ruiz | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
2025-11-12 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 230.72 |  |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Painting common areas 1st fl | [6 empty] | 160 |  |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting common areas 1st fl | [6 empty] | 160 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Oscar Giraldo | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Daniel Paucar | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Caulking | Alejandra Ramirez | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
| Caulking | Fabian Ruiz | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
| Ayudante | David Jhonson | 8 | 15 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 120
2025-11-13 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 230.72 | 88.66 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting common areas 1st fl | [6 empty] | 160 | 14.28 |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Daniel Paucar | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | Oscar Giraldo | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Caulking | Alejandra Ramirez | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
| Caulking | Fabian Ruiz | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
2025-11-14 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 230.72 | 44.34 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting common areas 1st fl | [6 empty] | 160 | 71.68 |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 | 139.41 |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Pintor | Daniel Paucar | 8 | 18.75 | David Rodriguez | Painting common areas 1st fl | [6 empty] | 150 |  |  | 8
| Caulking | Alejandra Ramirez | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
| Caulking | Fabian Ruiz | 8 | 15 | David Rodriguez | Caulking & putty units 3rd fl | [6 empty] | 120 |  |  | 8
2025-11-15 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting corridors 2nd Fl | [6 empty] | 230.72 | 200.65 |  | 8
| Superintendente | Bastian Sepulveda | 8 | 20 | David Rodriguez | Painting corridors 2nd Fl | [6 empty] | 160 |  |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting corridors 2nd Fl | [6 empty] | 200 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | David Rodriguez | Painting corridors 2nd Fl | [6 empty] | 150 |  |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | David Rodriguez | Painting corridors 2nd Fl | [6 empty] | 150 |  |  | 8
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | Painting corridors 2nd Fl | [6 empty] | 150 |  |  | 8
| Pintor | Daniel Paucar | 8 | 18.75 | David Rodriguez | Painting corridors 2nd Fl | [6 empty] | 150 |  |  | 8
| Pintor | Frank Coy | 8 | 18.75 | David Rodriguez | Painting corridors 2nd Fl | [6 empty] | 150 |  |  | 8
2025-11-17 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Painting trim units 3rd Fl | [6 empty] | 230.72 | 289.17 |  | 8
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | Painting trim units 3rd Fl | [6 empty] | 200 |  |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | David Rodriguez | Painting trim units 3rd Fl | [6 empty] | 150 |  |  | 8
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | Painting trim units 3rd Fl | [6 empty] | 150 |  |  | 8
| Pintor | Marvin Coy | 8 | 22.5 | David Rodriguez | Painting trim units 3rd Fl | [6 empty] | 180 |  |  | 8
2025-11-18 | PM | David Rodriguez | 9.5 | 28.84 | David Rodriguez | Painting corridors 3rd Fl | [6 empty] | 230.72 | 193.22 |  | 9.5
| Supervisor | Oscar Giraldo | 9.5 | 25 | Oscar Giraldo | Painting corridors 3rd Fl | [6 empty] | 200 | 21.15 |  | 9.5
| Pintor | Jorge Hernandez | 9.5 | 18.75 | David Rodriguez | Painting corridors 3rd Fl | [6 empty] | 178.2 | 295.53 |  | 9.5
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | Painting corridors 3rd Fl | [6 empty] | 150 |  |  | 8
| Pintor | Carlos Hernandez | 9.5 | 18.75 | David Rodriguez | Painting corridors 3rd Fl | [6 empty] | 178.2 |  |  | 9.5
2025-11-19 | Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | [7 empty] | 200 | 69.71 |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150 |  |  | 8
| Pintor | Elian Bonilla | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150 |  |  | 8
| Pintor | Osacar Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150 |  |  | 8
2025-11-20 | Supervisor | Oscar Giraldo | 8.5 | 25 | Oscar Giraldo | [7 empty] | 200 | 174.26 |  | 8.5
| Pintor | Jorge Hernandez | 8.5 | 18.75 | Oscar Giraldo | [7 empty] | 159.4 |  |  | 8.5
| Pintor | Elian Bonilla | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150 |  |  | 8
| Pintor | Carlos Hernandez | 8.5 | 18.75 | Oscar Giraldo | [7 empty] | 159.4 |  |  | 8.5
| Pintor | Osacar Hernandez | 8.5 | 18.75 | Oscar Giraldo | [7 empty] | 159.4 |  |  | 8
2025-11-21 | Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | [7 empty] | 200 |  |  | 8
| Pintor | Jorge Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150 |  |  | 8
| Pintor | Carlos Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150 |  |  | 8
| Pintor | Osacar Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150 |  |  | 8
2025-11-22 | Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | [7 empty] | 200 | 174.26
| Superintendente | Bastian Sepulveda | 8 | 20 | Oscar Giraldo | [7 empty] | 160
| Pintor | Jorge Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Carlos Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Osacar Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Frank Coy | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
2024-11-24 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | [7 empty] | 200
| Pintor | Jorge Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Carlos Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Osacar Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
2025-11-25 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72 | 174.26
| Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | [7 empty] | 200 | 17.96
| Pintor | Jorge Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Carlos Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Osacar Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Elian Bonilla | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
2025-11-26 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72 | 104.56
| Supervisor | Oscar Giraldo | 8 | 25 | David Rodriguez | [7 empty] | 200 | 27.81
| Superintendente | Bastian Sepulveda | 8 | 20 | David Rodriguez | [7 empty] | 160
| Pintor | Jorge Hernandez | 8 | 18.75 | David Rodriguez | [7 empty] | 150
| Pintor | Carlos Hernandez | 8 | 18.75 | David Rodriguez | [7 empty] | 150
| Pintor | Osacar Hernandez | 8 | 18.75 | David Rodriguez | [7 empty] | 150
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | [7 empty] | 150
2025-11-28 | Supervisor | Oscar Giraldo | 8 | 25 | Oscar Giraldo | [7 empty] | 200
| Superintendente | Bastian Sepulveda | 8 | 20 | Oscar Giraldo | [7 empty] | 160
| Pintor | Jorge Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Carlos Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Osacar Hernandez | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Elian Bonilla | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
| Pintor | Frank Coy | 8 | 18.75 | Oscar Giraldo | [7 empty] | 150
2025-12-01 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72 | 34.85
| Supervisor | Oscar Giraldo | 8 | 25 | David Rodriguez | [7 empty] | 200
| Superintendente | Bastian Sepulveda | 8 | 20 | David Rodriguez | [7 empty] | 160
| Pintor | Jorge Hernandez | 8 | 18.75 | David Rodriguez | [7 empty] | 150
| Pintor | Carlos Hernandez | 8 | 18.75 | David Rodriguez | [7 empty] | 150
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | [7 empty] | 150
2025-12-02 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Superintendente | Bastian Sepulveda | 8 | 20 | David Rodriguez | [7 empty] | 160
| Pintor | Jorge Hernandez | 8 | 18.75 | David Rodriguez | [7 empty] | 150
| Pintor | Carlos Hernandez | 8 | 18.75 | David Rodriguez | [7 empty] | 150
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | [7 empty] | 150
| Pintor | Osacar Hernandez | 8 | 18.75 | David Rodriguez | [7 empty] | 150
2025-12-03 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | [7 empty] | 150
2025-12-04 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Pintor | Elian Bonilla | 8 | 18.75 | David Rodriguez | [7 empty] | 150
Birchwood Lighthouse - 1150 Norton Ave - Ingerman |  |  |  |  | David Rodriguez | Final Cleaning | 100% |  |  | 383.4 |  | 11572 | 12884.21 | 260.14 | 536 | 696
2025-10-14 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Rough Clean units 1st floor | [6 empty] | 160 |  |  | 8
| Cleaner | Elian David | 8 | 15 | Bastian Sepulveda | Rough Clean units 1st floor | [6 empty] | 120 |  |  | 8
| Cleaner | Ana | 8 | 15 | Bastian Sepulveda | Rough Clean units 1st floor | [6 empty] | 120 |  |  | 8
| Cleaner | Carlos | 8 | 15 | Bastian Sepulveda | Rough Clean units 1st floor | [6 empty] | 120 |  |  | 8
2025-10-15 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Rough Clean units 1st floor | [6 empty] | 160 |  |  | 8
| Cleaner | Ana | 8 | 15 | Bastian Sepulveda | Rough Clean units 1st floor | [6 empty] | 120 |  |  | 8
2025-10-23 | PM | David Rodriguez | 8 | 28.84 | Bastian Sepulveda | Rough Clean units 2dnd Floor | [6 empty] | 230.72 | 54.75 |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | Bastian Sepulveda | Rough Clean units 2dnd Floor | [6 empty] | 150 |  |  | 8
| Cleaner | Frank Coy | 8 | 12 | Bastian Sepulveda | Rough Clean units 2dnd Floor | [6 empty] | 120 |  |  | 8
2025-10-27 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Final Clean units 1st floor | [6 empty] | 160 | 76.76 |  | 8
| Cleaner | Ana Mendoza | 8 | 15 | Bastian Sepulveda | Final Clean units 1st floor | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | Bastian Sepulveda | Final Clean units 1st floor | [6 empty] | 120 |  |  | 8
2025-10-28 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Final Clean units 1st floor | [6 empty] | 160 |  |  | 8
| Cleaner | Ana Mendoza | 8 | 15 | Bastian Sepulveda | Final Clean units 1st floor | [6 empty] | 120 | 68.82 | squeegee | 8
2025-11-10 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 120 |  |  | 8
| Cleaner | Maria Velandia | 8 | 15 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 120 |  |  | 8
2025-11-11 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 120 |  |  | 8
2025-11-12 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 120 |  |  | 8
2025-11-13 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Clean common areas 1st floor | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Clean common areas 1st floor | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Clean common areas 1st floor | [6 empty] | 120 |  |  | 8
2025-11-14 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean units 2dn floor | [6 empty] | 120 |  |  | 8
2025-11-17 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch up units 1st FL | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Touch up units 1st FL | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Touch up units 1st FL | [6 empty] | 120 |  |  | 8
2025-11-18 | PM | David Rodriguez | 9.5 | 28.84 | David Rodriguez | Touch up units 1st FL | [6 empty] | 230.72 |  |  | 9.5
| Cleaner | Diana Diaz | 9.5 | 15 | David Rodriguez | Touch up units 1st FL | [6 empty] | 142.5 |  |  | 9.5
| Cleaner | Camila Cardenas | 9,5 | 15 | David Rodriguez | Touch up units 1st FL | [6 empty] | 142.5 |  |  | 9.5
| Cleaner | Christofer | 5 | 15 | David Rodriguez | Touch up units 1st FL | [6 empty] | 75 |  |  | 5
2025-11-19 | Supervisor | Martha Rios | 8 | 18.75 | Martha Rios | Touch up units 1st FL | [6 empty] | 150 |  |  | 8
| Cleaner | Christofer | 8 | 15 | Martha Rios | Touch up units 1st FL | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | Martha Rios | Touch up units 1st FL | [6 empty] | 120 |  |  | 8
2025-11-20 | Supervisor | Martha Rios | 8 | 18.75 | Martha Rios | Touch up units 1st FL | [6 empty] | 150 |  |  | 8
| Cleaner | Christofer | 8 | 15 | Martha Rios | Touch up units 1st FL | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | Martha Rios | Touch up units 1st FL | [6 empty] | 120 |  |  | 8
| Cleaner | Alejandra Ramirez | 8 | 15 | Martha Rios | Touch up units 1st FL | [6 empty] | 120
2025-11-21 | Supervisor | Martha Rios | 8 | 18.75 | Martha Rios | Touch up units 1st FL | [6 empty] | 150
| Cleaner | Christofer | 8 | 15 | Martha Rios | Touch up units 1st FL | [6 empty] | 120
| Cleaner | Malbira Pereira | 8 | 15 | Martha Rios | Touch up units 1st FL | [6 empty] | 120
| Cleaner | Wilmary | 8 | 15 | Martha Rios | Touch up units 1st FL | [6 empty] | 120
| Cleaner | Josly | 8 | 15 | Martha Rios | [7 empty] | 120
| Cleaner | Natalia | 8 | 15 | Martha Rios | [7 empty] | 120
| Cleaner | Kahhim | 8 | 15 | Martha Rios | [7 empty] | 120
2025-11-24 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Malbira Pereira | 8 | 15 | Martha Rios | [7 empty] | 120
| Cleaner | Christofer | 8 | 15 | Martha Rios | [7 empty] | 120
2025-11-25 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Christofer | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Josly | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Natalia | 8 | 15 | David Rodriguez | [7 empty] | 120
2025-11-26 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Christofer | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Viviana (Ecuador) | 8 | 15 | David Rodriguez | [7 empty] | 120
2025-11-28 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
|  | Christofer | 8 | 15 | David Rodriguez | [7 empty] | 120
2025-12-01 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Cleaner | Christofer | 8 | 15 | David Rodriguez | [7 empty] | 120
2025-12-02 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Cleaner | Christofer | 8 | 15 | David Rodriguez | [7 empty] | 120
2025-12-03 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Cleaner | Christofer | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | [7 empty] | 120
2025-12-04 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72 | 59.81
| Cleaner | Christofer | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | [7 empty] | 120
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | [7 empty] | 120
2025-12-05 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Cleaner | Christofer | 2 | 17.5 | David Rodriguez | [7 empty] | 35
| Cleaner | Elian Bonilla | 4 | 18.75 | David Rodriguez | [7 empty] | 75
2025-12-08 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | [7 empty] | 230.72
| Cleaner | Christofer | 5 | 17.5 | David Rodriguez | [7 empty] | 87.5
| Cleaner | Elian Bonilla | 5 | 18.75 | David Rodriguez | [7 empty] | 93.75
Birchwood Lighthouse - 1150 Norton Ave - Ingerman |  |  |  |  | David Rodriguez | Change Order | 100% | [5 empty] | 1520 | 118.13 |  | 80
2025-07-28 | PM | David Rodriguez | 8 | 27.5 | David Rodriguez | Construction Cleaning | [6 empty] | 220 | 83.13 |  | 8
2025-07-28 | Cleaner | Brahian Zamora | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120 |  |  | 8
2025-07-29 | Cleaner | Brahian Zamora | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120 |  |  | 8
2025-07-29 | Cleaner | Sebastian Hidalgo | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120 |  |  | 8
2025-07-30 | Supervisor | Oscar Giraldo | 8 | 25 | David Rodriguez | Construction Cleaning | [6 empty] | 200 |  |  | 8
2025-07-30 | Cleaner | Cesar Rico | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120 |  |  | 8
2025-07-30 | Cleaner | Sandra Celis | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120 |  |  | 8
2025-08-15 | Supervisor | Oscar Giraldo | 8 | 25 | David Rodriguez | Construction Cleaning | [6 empty] | 200 |  |  | 8
2025-09-10 | Cleaner | Elian David | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120 |  |  | 8
2025-09-19 | Cleaner | Elian David | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120 |  |  | 8
2025-09-08 | Caulkin | Elian David | 4 | 15 | David Rodriguez | Caulkin countertop & vanity | [6 empty] | 60 | 35 |  | 4
20-30 W Allens - 20 West Allens Lane - TCG Tester Construction Group |  |  |  |  | David Rodriguez | Final Cleaning | 100% |  |  | 309.8 |  | 14179 | 13758.16 | 265.7 | 320 | 742.5
2025-10-16 | PM | David Rodriguez | 4 | 28.84 | Bastian Sepulveda | Rough Clean Floor 4 | [6 empty] | 115.36 |  |  | 4
| Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Rough Clean Floor 4 | [6 empty] | 160 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | Bastian Sepulveda | Rough Clean Floor 4 | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | Bastian Sepulveda | Rough Clean Floor 4 | [6 empty] | 120 |  |  | 8
| Cleaner | Carla Sepulveda | 8 | 15 | Bastian Sepulveda | Rough Clean Floor 4 | [6 empty] | 120 |  |  | 8
2025-10-17 | Superintendente | Bastian Sepulveda | 10 | 20 | Bastian Sepulveda | Rough Clean Floor 4 | [6 empty] | 200 |  |  | 10
| Cleaner | Diana Diaz | 10 | 15 | Bastian Sepulveda | Rough Clean Floor 4 | [6 empty] | 150 |  |  | 10
| Cleaner | Camila Cardenas | 10 | 15 | Bastian Sepulveda | Rough Clean Floor 4 | [6 empty] | 150 |  |  | 10
| Cleaner | Carla Sepulveda | 10 | 15 | Bastian Sepulveda | Rough Clean Floor 4 | [6 empty] | 150 |  |  | 10
2025-10-23 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Rough Clean Floor 3 | [6 empty] | 160 | 69.36 |  | 8
| Cleaner | Diana Diaz | 8 | 15 | Bastian Sepulveda | Rough Clean Floor 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 12 | Bastian Sepulveda | Rough Clean Floor 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Ana Mendoza | 8 | 12 | Bastian Sepulveda | Rough Clean Floor 3 | [6 empty] | 120 |  |  | 8
2025-10-24 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Rough Clean Floor 3 | [6 empty] | 160 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | Bastian Sepulveda | Rough Clean Floor 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 12 | Bastian Sepulveda | Rough Clean Floor 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Ana Mendoza | 8 | 12 | Bastian Sepulveda | Rough Clean Floor 3 | [6 empty] | 120 |  |  | 8
2025-11-03 | Superintendente | Bastian Sepulveda | 8 | 20 | Bastian Sepulveda | Rough Clean Floor 2 | [6 empty] | 160 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | Bastian Sepulveda | Rough Clean Floor 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 12 | Bastian Sepulveda | Rough Clean Floor 2 | [6 empty] | 120 |  |  | 8
2025-11-04 | Superintendente | Bastian Sepulveda | 10 | 20 | Bastian Sepulveda | Rough Clean Floor 2 | [6 empty] | 200 |  |  | 10
| Cleaner | Diana Diaz | 10 | 15 | Bastian Sepulveda | Rough Clean Floor 2 | [6 empty] | 150 |  |  | 10
| Cleaner | Malbira Pereira | 10 | 15 | Bastian Sepulveda | Rough Clean Floor 2 | [6 empty] | 150 |  |  | 10
| Cleaner | Dora | 10 | 15 | Bastian Sepulveda | Rough Clean Floor 2 | [6 empty] | 150 |  |  | 10
| Cleaner | Viviana | 10 | 15 | Bastian Sepulveda | Rough Clean Floor 2 | [6 empty] | 150 |  |  | 10
2025-12-15 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Rough Clean Floor 1 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Rough Clean Floor 1 | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Rough Clean Floor 1 | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Rough Clean Floor 1 | [6 empty] | 120 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Rough Clean Floor 1 | [6 empty] | 150 |  |  | 8
2025-12-16 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean Floor 3 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean Floor 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Final Clean Floor 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean Floor 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Final Clean Floor 3 | [6 empty] | 150 |  |  | 8
2025-12-17 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean Floor 3 & 2 | [6 empty] | 230.72 | 114.33 | Home Depot Materials | 8
| Cleaner | Diana Diaz | 8 | 15 | David Rodriguez | Final Clean Floor 3 & 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Final Clean Floor 3 & 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Camila Cardenas | 8 | 15 | David Rodriguez | Final Clean Floor 3 & 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Final Clean Floor 3 & 2 | [6 empty] | 150 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Final Clean Floor 3 & 2 | [6 empty] | 200 |  |  | 8
| Cleaner | Viviana | 8 | 15 | David Rodriguez | Final Clean Floor 3 & 2 | [6 empty] | 120 |  |  | 8
2025-12-18 | PM | David Rodriguez | 10 | 28.84 | David Rodriguez | Final Clean Floor 2 & lobby | [6 empty] | 230.72 |  |  | 10
| Cleaner | Diana Diaz | 10 | 15 | David Rodriguez | Final Clean Floor 2 & lobby | [6 empty] | 150 |  |  | 10
| Cleaner | Malbira Pereira | 10 | 15 | David Rodriguez | Final Clean Floor 2 & lobby | [6 empty] | 150 |  |  | 10
| Cleaner | Camila Cardenas | 10 | 15 | David Rodriguez | Final Clean Floor 2 & lobby | [6 empty] | 150 |  |  | 10
| Cleaner | Elian Bonilla | 10 | 18.75 | David Rodriguez | Final Clean Floor 2 & lobby | [6 empty] | 150 |  |  | 10
| Cleaner | Oscar Giraldo | 10 | 25 | David Rodriguez | Final Clean Floor 2 & lobby | [6 empty] | 200 |  |  | 10
| Cleaner | Fernanda Hormaza | 10 | 15 | David Rodriguez | Final Clean Floor 2 & lobby | [6 empty] | 150 |  |  | 10
2026-01-12 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean Floor 4 | [6 empty] | 230.72 | 82.01 |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Final Clean Floor 4 | [6 empty] | 200 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Final Clean Floor 4 | [6 empty] | 150 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Final Clean Floor 4 | [6 empty] | 120 |  |  | 8
| Cleaner | Fernanda Hormaza | 8 | 15 | David Rodriguez | Final Clean Floor 4 | [6 empty] | 120 |  |  | 8
2026-01-13 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean Floor 4 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Final Clean Floor 4 | [6 empty] | 200 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 18.75 | David Rodriguez | Final Clean Floor 4 | [6 empty] | 150 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Final Clean Floor 4 | [6 empty] | 120 |  |  | 8
| Cleaner | Fernanda Hormaza | 8 | 15 | David Rodriguez | Final Clean Floor 4 | [6 empty] | 120 |  |  | 8
2026-01-16 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch up Floor 2 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Touch up Floor 2 | [6 empty] | 200 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 15 | David Rodriguez | Touch up Floor 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Touch up Floor 2 | [6 empty] | 120 |  |  | 8
| Cleaner | Grazi | 8 | 15 | David Rodriguez | Touch up Floor 2 | [6 empty] | 120 |  |  | 8
2026-01-21 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch up Floor 3 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Touch up Floor 3 | [6 empty] | 200 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 15 | David Rodriguez | Touch up Floor 3 | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Touch up Floor 3 | [6 empty] | 120 |  |  | 8
2026-01-22 | PM | David Rodriguez | 5 | 28.84 | David Rodriguez | Touch up Floor 3 | [6 empty] | 119.2 |  |  | 5
| Cleaner | Oscar Giraldo | 5 | 25 | David Rodriguez | Touch up Floor 3 | [6 empty] | 125 |  |  | 5
| Cleaner | Elian Bonilla | 5 | 15 | David Rodriguez | Touch up Floor 3 | [6 empty] | 75 |  |  | 5
| Cleaner | Malbira Pereira | 5 | 15 | David Rodriguez | Touch up Floor 3 | [6 empty] | 75 |  |  | 5
2026-01-29 | PM | David Rodriguez | 9.5 | 28.84 | David Rodriguez | Final Clean Floor 1 | [6 empty] | 230.72 |  |  | 9.5
| Cleaner | Viviana Once | 9.5 | 15 | David Rodriguez | Final Clean Floor 1 | [6 empty] | 142.5 |  |  | 9.5
| Cleaner | Elian Bonilla | 9.5 | 15 | David Rodriguez | Final Clean Floor 1 | [6 empty] | 142.5 |  |  | 9.5
| Cleaner | Graziele Arruda | 9.5 | 15 | David Rodriguez | Final Clean Floor 1 | [6 empty] | 142.5 |  |  | 9.5
2026-02-11 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch up Floor 4 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Touch up Floor 4 | [6 empty] | 200 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 15 | David Rodriguez | Touch up Floor 4 | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Touch up Floor 4 | [6 empty] | 120 |  |  | 8
2026-02-12 | PM | David Rodriguez | 6 | 28.84 | David Rodriguez | Touch up Floor 4 | [6 empty] | 173.04 |  |  | 6
| Cleaner | Elian Bonilla | 6 | 15 | David Rodriguez | Touch up Floor 4 | [6 empty] | 90 |  |  | 6
| Cleaner | Malbira Pereira | 6 | 15 | David Rodriguez | Touch up Floor 4 | [6 empty] | 90 |  |  | 6
2026-02-19 | PM | David Rodriguez | 8.5 | 28.84 | David Rodriguez | Touch up Floor 1 | [6 empty] | 245.14 |  |  | 8.5
| Cleaner | Oscar Giraldo | 8.5 | 25 | David Rodriguez | Touch up Floor 1 | [6 empty] | 212.5 |  |  | 8.5
| Cleaner | Elian Bonilla | 7.5 | 15 | David Rodriguez | Touch up Floor 1 | [6 empty] | 112.5 |  |  | 7.5
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Touch up Floor 1 | [6 empty] | 120 |  |  | 8
2026-02-20 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Clean Common Areas | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Clean Common Areas | [6 empty] | 200 |  |  | 8
| Cleaner | Elian Bonilla | 7 | 15 | David Rodriguez | Clean Common Areas | [6 empty] | 105 |  |  | 7
| Cleaner | Malbira Pereira | 7 | 15 | David Rodriguez | Clean Common Areas | [6 empty] | 105 |  |  | 7
Christ Home Cottages - Harkins Builders |  |  |  |  | David Rodriguez | Final Cleaning | 100% |  |  | 310 |  | 1626 | 3075.48 |  | 320 | 130.5
2025-12-08 | PM | David Rodriguez | 5 | 28.84 | David Rodriguez | Rough clean unit 590/592 | [6 empty] | 144.2 |  |  | 5
| Cleaner | Christofer | 4 | 17.5 | David Rodriguez | Rough clean unit 590/592 | [6 empty] | 70 |  |  | 4
| Cleaner | Elian Bonilla | 5 | 18.75 | David Rodriguez | Rough clean unit 590/592 | [6 empty] | 93.75 |  |  | 5
2025-12-11 | PM | David Rodriguez | 5 | 28.84 | David Rodriguez | Rough clean unit 580/582 | [6 empty] | 144.2 |  |  | 5
| Cleaner | Oscar Giraldo | 5 | 25 | David Rodriguez | Rough clean unit 580/582 | [6 empty] | 125 |  |  | 5
| Cleaner | Elian Bonilla | 5 | 18.75 | David Rodriguez | Rough clean unit 580/582 | [6 empty] | 93.75 |  |  | 5
2025-12-19 | PM | David Rodriguez | 5 | 28.84 | David Rodriguez | Rough clean unit 570/572 | [6 empty] | 144.2 |  |  | 5 |  | Paid
| Cleaner | Oscar Giraldo | 5 | 25 | David Rodriguez | Rough clean unit 570/572 | [6 empty] | 125 |  |  | 5
| Cleaner | Elian Bonilla | 5 | 15 | David Rodriguez | Rough clean unit 570/572 | [6 empty] | 75 |  |  | 5
2026-02-10 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final clean unit 590/592 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Final clean unit 590/592 | [6 empty] | 200 |  |  | 8
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Final clean unit 590/592 | [6 empty] | 120 |  |  | 8
2026-03-04 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final clean unit 580/582 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Final clean unit 580/582 | [6 empty] | 200 |  |  | 8
| Cleaner | Elian Bonilla | 8 | 15 | David Rodriguez | Final clean unit 580/582 | [6 empty] | 120 |  |  | 8
2026-03-11 | PM | David Rodriguez | 6.5 | 28.84 | David Rodriguez | Final clean unit 570/572 | [6 empty] | 187.46 |  |  | 6.5 |  | Paid
| Cleaner | Oscar Giraldo | 6.5 | 25 | David Rodriguez | Final clean unit 570/572 | [6 empty] | 162.5 |  |  | 6.5
| Cleaner | Elian Bonilla | 6.5 | 15 | David Rodriguez | Final clean unit 570/572 | [6 empty] | 97.5 |  |  | 6.5
2026-03-30 | PM | David Rodriguez | 9.5 | 28.84 | David Rodriguez | Touch of up all 6 units | [6 empty] | 273.98 |  |  | 9.5
| Cleaner | Oscar Giraldo | 9.5 | 25 | David Rodriguez | Touch of up all 6 units | [6 empty] | 237.5 |  |  | 9.5
Christ Home Cottages - Harkins Builders |  |  |  |  | David Rodriguez | Change Order | 100% | [5 empty] | 320.18 |  |  | 14 | 100% | Billing
2026-04-06 | PM | David Rodriguez | 2 | 28.84 | David Rodriguez | Power-washing | [6 empty] | 57.68 |  |  | 2
| Cleaner | Oscar Giraldo | 6 | 25 | David Rodriguez | Power-washing | [6 empty] | 150 |  |  | 6
| Cleaner | William Sotelo | 6 | 18.75 | David Rodriguez | Power-washing | [6 empty] | 112.5 |  |  | 6
498 Red Apple Ct, Central Valley, NY 10917 PUMA STORE DW1 |  |  |  |  | David Rodriguez | Final Cleaning | 100% | [5 empty] | 735.53 |  |  | 33.5
2026-04-30 | PM | David Rodriguez | 4 | 28.84 | David Rodriguez | Clean PUMA Store NY | [6 empty] | 115.36 |  |  | 4
| Cleaner | Oscar Giraldo | 4 | 25 | David Rodriguez | Clean PUMA Store NY | [6 empty] | 100 |  |  | 4
| Cleaner | Zakeem Doughty | 4 | 20 | David Rodriguez | Clean PUMA Store NY | [6 empty] | 80 |  |  | 4
| Cleaner | Don Albeiro | 4 | 18 | David Rodriguez | Clean PUMA Store NY | [6 empty] | 72 |  |  | 4
2026-05-01 | PM | David Rodriguez | 3.5 | 28.84 | David Rodriguez | Clean PUMA Store NY | [6 empty] | 100.94 |  |  | 3.5
| Cleaner | Oscar Giraldo | 3.5 | 25 | David Rodriguez | Clean PUMA Store NY | [6 empty] | 87.5 |  |  | 3.5
| Cleaner | Arelis Campaz | 3.5 | 16.35 | David Rodriguez | Clean PUMA Store NY | [6 empty] | 57.225 |  |  | 3.5
| Cleaner | Hijo Arelis | 3.5 | 15 | David Rodriguez | Clean PUMA Store NY | [6 empty] | 52.5 |  |  | 3.5
| Cleaner | Jahbulani Shawn | 3.5 | 20 | David Rodriguez | Clean PUMA Store NY | [6 empty] | 70 |  |  | 3.5
Saddle Brook - BLOCK 1401, LOT 18 - Ingerman |  |  |  |  | David Rodriguez | Final Cleaning | 10% |  |  | 310 |  | 16972 | 1076.32 |  | 320 | 24
2026-05-04 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 230.72 |  |  | 8
| Cleaner | Albeiro Canas | 8 | 18 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 144 |  |  | 8
| Cleaner | Jahbulani Shawn | 8 | 20 | David Rodriguez | Rough Clean Building 3 | [6 empty] | 160 |  |  | 8
2026-05-05 | PM | Kathrine Rojas | 8 | 20 | Kathrine Rojas | Rough Clean Building 3 | [6 empty] | 160 |  |  | 8
| Cleaner | Derly Garzon | 8 | 16.35 | Kathrine Rojas | Rough Clean Building 3 | [6 empty] | 130.8 |  |  | 8
| Cleaner | Arelis Campaz | 8 | 16.35 | Kathrine Rojas | Rough Clean Building 3 | [6 empty] | 130.8 |  |  | 8
| Cleaner | Jeanette | 8 | 15 | Kathrine Rojas | Rough Clean Building 3 | [6 empty] | 120 |  |  | 8
Saddle Brook - BLOCK 1401, LOT 18 - Ingerman |  |  |  |  | David Rodriguez | Change Order | 100% | [5 empty] | 1672.24 |  |  | 155.5 | 100% | Billing
2025-12-22 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Construction Cleaning | [6 empty] | 230.72
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Construction Cleaning | [6 empty] | 200
| Cleaner | Elian Bonilla | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120
2026-03-16 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Construction Cleaning | [6 empty] | 230.72
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Construction Cleaning | [6 empty] | 200
| Cleaner | Malbira Pereira | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120
2026-03-17 | PM | David Rodriguez | 6.5 | 28.84 | David Rodriguez | Construction Cleaning | [6 empty] | 187.46
| Cleaner | Oscar Giraldo | 6.5 | 25 | David Rodriguez | Construction Cleaning | [6 empty] | 162.5
| Cleaner | William Sotelo | 6.5 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 97.5
2026-04-13 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Construction Cleaning | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Construction Cleaning | [6 empty] | 200 |  |  | 8
| Cleaner | William Sotelo | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | James Warthem | 8 | 16.35 | David Rodriguez | Construction Cleaning | [6 empty] | 130.8 |  |  | 8
| Cleaner | Arelis Campaz | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120 |  |  | 8
2026-04-14 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Construction Cleaning | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Construction Cleaning | [6 empty] | 200 |  |  | 8
| Cleaner | Zakeem Doughty | 8 | 20 | David Rodriguez | Construction Cleaning | [6 empty] | 160 |  |  | 8
| Cleaner | Franklin Olivares | 8 | 20 | David Rodriguez | Construction Cleaning | [6 empty] | 160 |  |  | 8
| Cleaner | Arelis Campaz | 8 | 15 | David Rodriguez | Construction Cleaning | [6 empty] | 120 |  |  | 8
2026-05-01 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Construction Cleaning Tubs/Showers/ gabinets/windows | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Construction Cleaning Tubs/Showers/ gabinets/windows | [6 empty] | 200 |  |  | 8
| Cleaner | Jahbulani Shawn | 8 | 20 | David Rodriguez | Construction Cleaning Tubs/Showers/ gabinets/windows | [6 empty] | 160 |  |  | 8
| Cleaner | Andres Campaz | 8 | 15 | David Rodriguez | Construction Cleaning Tubs/Showers/ gabinets/windows | [6 empty] | 120 |  |  | 8
| Cleaner | Arelis Campaz | 8 | 16.35 | David Rodriguez | Construction Cleaning Tubs/Showers/ gabinets/windows | [6 empty] | 130.8 |  |  | 8
The Mercer - 50 26th Street - Franjo Construction (PITTSBURGH) |  |  |  |  | David Rodriguez | Final Cleaning | 8% |  |  |  |  | 55395 | 7398.72 | 1366.87 |  | 40
2026-05-12 | PM | David Rodriguez | 10 | 28.84 | David Rodriguez | Final Clean 2nd Floor | [6 empty] | 288.4 | 840.18 |  | 8
| Cleaner | Benjamin | 10 | 15 | David Rodriguez | Final Clean 2nd Floor | [6 empty] | 150 |  |  | 8
| Contratista | Pedro | 10 |  | David Rodriguez | Final Clean 2nd Floor 10 units | [6 empty] | 712 |  |  | 10
2026-05-13 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean 2nd Floor | [6 empty] | 230.72 |  |  | 8
| Cleaner | Benjamin | 8 | 15 | David Rodriguez | Final Clean 2nd Floor | [6 empty] | 120 |  |  | 8
| Contratista | Pedro | 8 |  | David Rodriguez | Final Clean 2nd Floor 9 units | [6 empty] | 628 |  |  | 8
2026-05-14 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean 2nd Floor | [6 empty] | 230.72 |  |  | 8
| Cleaner | Benjamin | 8 | 15 | David Rodriguez | Final Clean 2nd Floor | [6 empty] | 120 |  |  | 8
| Contratista | Pedro | 8 |  | David Rodriguez | Final Clean 2nd Floor 9 units | [6 empty] | 612 |  |  | 8
2026-05-15 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Final Clean 2nd Floor | [6 empty] | 230.72 |  |  | 8
| Cleaner | Benjamin | 4 | 15 | David Rodriguez | Final Clean 2nd Floor | [6 empty] | 60 |  |  | 8
| Contratista | Pedro | 8 |  | David Rodriguez | Final Clean 2nd Floor 8 units | [6 empty] | 576 |  |  | 8
2026-05-19 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch-up 2nd Floor | [6 empty] | 230.72 | 526.69 |  | 8
| Contratista | Pedro | 8 |  | David Rodriguez | Touch-up 2nd Floor 13 units | [6 empty] | 916
2026-05-20 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch-up 2nd Floor | [6 empty] | 230.72 |  |  | 8
| Contratista | Pedro | 8 |  | David Rodriguez | Touch-up 2nd Floor 15 units | [6 empty] | 1020
2026-05-21 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Touch-up 2nd Floor | [6 empty] | 230.72 |  |  | 8
| Contratista | Pedro | 8 |  | David Rodriguez | Touch-up 2nd Floor 11 units | [6 empty] | 812
The Mercer - 50 26th Street - Franjo Construction (PITTSBURGH) |  |  |  |  | David Rodriguez | Change Order | 0% |  |  |  |  | 55395 | 1624.64 | 961.02 |  | 40
2026-05-07 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Rough Clean 2nd Floor | [6 empty] | 230.72 | 961.02 |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Rough Clean 2nd Floor | [6 empty] | 200 |  |  | 8
| Cleaner | Derly Garzon | 8 | 16.35 | David Rodriguez | Rough Clean 2nd Floor | [6 empty] | 130.8 |  |  | 8
| Cleaner | Areliz Campaz | 8 | 16.35 | David Rodriguez | Rough Clean 2nd Floor | [6 empty] | 130.8 |  |  | 8
| Cleaner | Jeanette | 8 | 15 | David Rodriguez | Rough Clean 2nd Floor | [6 empty] | 120 |  |  | 8
2026-05-08 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Rough Clean 2nd Floor | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Rough Clean 2nd Floor | [6 empty] | 200 |  |  | 8
| Cleaner | Derly Garzon | 8 | 16.35 | David Rodriguez | Rough Clean 2nd Floor | [6 empty] | 130.8 |  |  | 8
| Cleaner | Areliz Campaz | 8 | 16.35 | David Rodriguez | Rough Clean 2nd Floor | [6 empty] | 130.8 |  |  | 8
| Cleaner | Jeanette | 8 | 15 | David Rodriguez | Rough Clean 2nd Floor | [6 empty] | 120 |  |  | 8
Brightview, Brick, NJ - 1568 New Jersey 88 - Harkins Builders |  |  |  |  | David Rodriguez | Change Order | 100% |  |  |  |  | 3440 | 1611.44 |  |  | 72 | 100% | Billing
2026-04-02 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Construction Cleaning | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Construction Cleaning | [6 empty] | 200 |  |  | 8
| Cleaner | Home Depot Labor | 8 | 18.75 | David Rodriguez | Construction Cleaning | [6 empty] | 150 |  |  | 8
| Cleaner | Home Depot Labor | 8 | 18.75 | David Rodriguez | Construction Cleaning | [6 empty] | 150 |  |  | 8
2026-04-03 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Construction Cleaning | [6 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Construction Cleaning | [6 empty] | 200 |  |  | 8
| Cleaner | William Sotelo | 8 | 18.75 | David Rodriguez | Construction Cleaning | [6 empty] | 150 |  |  | 8
| Cleaner | Home Depot Labor | 8 | 18.75 | David Rodriguez | Construction Cleaning | [6 empty] | 150 |  |  | 8
| Cleaner | Home Depot Labor | 8 | 18.75 | David Rodriguez | Construction Cleaning | [6 empty] | 150 |  |  | 8
2026-05-01 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Construction Cleaning | [6 empty] | 230.72 |  |  | 8
| Cleaner | Zakeem Doughty | 8 | 20 | David Rodriguez | Construction Cleaning | [6 empty] | 160 |  |  | 8
| Cleaner | Jahbulani Shawn | 8 | 20 | David Rodriguez | Construction Cleaning | [6 empty] | 160 |  |  | 8
| Cleaner | Albeiro Canas | 8 | 18 | David Rodriguez | Construction Cleaning | [6 empty] | 144 |  |  | 8
Spruce Run - BLOCK 70, LOTS G & G.01 ROUTE 31CLINTON TOWNSHIP, NJ - Ingerman |  |  |  |  | David Rodriguez | Final Cleaning | 0% |  |  |  |  | 28560
Spruce Run - BLOCK 70, LOTS G & G.01 ROUTE 31CLINTON TOWNSHIP, NJ - Ingerman |  |  |  |  | David Rodriguez | Change Order | [6 empty] | 508.9 |  |  | 28
2026-05-15 | Supervisor | Katherine Rojas | 7 | 20 | Katherine Rojas | Construction Cleaning | [6 empty] | 140 |  |  | 7
| Cleaner | Malbira Pereira | 7 | 16.35 | Katherine Rojas | Construction Cleaning | [6 empty] | 114.45 |  |  | 7
| Cleaner | Anthony Boyd | 7 | 16.35 | Katherine Rojas | Construction Cleaning | [6 empty] | 114.45 |  |  | 7
| Cleaner | Oscar Giraldo | 7 | 20 | Katherine Rojas | Construction Cleaning | [6 empty] | 140 |  |  | 7
EW Rhodes Elementary School, 2900 W Clearfield Street, Philadelphia PA 19130 - Smith Construction, Inc. |  |  |  |  | David Rodriguez | Final Cleaning | 80% |  |  |  |  | 6039 | 2843.2 |  |  | 168
2026-05-11 | Supervisor | Katherine Rojas | 8 | 20 | Katherine Rojas | Final Cleaning | [6 empty] | 160 |  |  | 8
| Cleaner | Valery | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Anyela | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Oscar | 8 | 25 | Katherine Rojas | Final Cleaning | [6 empty] | 200 |  |  | 8
| Cleaner | Anthony | 8 | 16.35 | Katherine Rojas | Final Cleaning | [6 empty] | 130.8 |  |  | 8
| Cleaner | Achanti | 8 | 20 | Katherine Rojas | Final Cleaning | [6 empty] | 160 |  |  | 8
2026-05-12 | Supervisor | Katherine Rojas | 8 | 20 | Katherine Rojas | Final Cleaning | [6 empty] | 160 |  |  | 8
| Cleaner | Valery | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Anyela | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Achanti | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira | 8 | 16.35 | Katherine Rojas | Final Cleaning | [6 empty] | 130.8 |  |  | 8
2026-05-13 | Supervisor | Katherine Rojas | 8 | 20 | Katherine Rojas | Final Cleaning | [6 empty] | 160 |  |  | 8
| Cleaner | Valery | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Flor | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Achanti | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Anthony | 8 | 16.35 | Katherine Rojas | Final Cleaning | [6 empty] | 130.8 |  |  | 8
2026-05-14 | Supervisor | Katherine Rojas | 8 | 20 | Katherine Rojas | Final Cleaning | [6 empty] | 160 |  |  | 8
| Cleaner | Valery | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Anyela | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Achanti | 8 | 15 | Katherine Rojas | Final Cleaning | [6 empty] | 120 |  |  | 8
| Cleaner | Anthony | 8 | 16.35 | Katherine Rojas | Final Cleaning | [6 empty] | 130.8 |  |  | 8
Brightview, Brick, NJ - 1568 New Jersey 88 - Harkins Builders |  |  |  |  | David Rodriguez | Final Painting | 0% |  |  | 36021 |  | 97420
Nittany Apartments - Penn State Schuylkill - Turns |  |  |  |  | David Rodriguez | Turnover Cleaning | 0% |  |  |  |  | 14094
Tempo Hotel Bethlehem - West 3rd Street Bethlehem, PA 18015 - High Construction Company |  |  |  |  | David Rodriguez | Final Cleaning | 0% |  |  |  |  | 26750
2026-05-11 | PM | Katherine Rojas | 8 | 20 | Katherine Rojas | Construction Clean | [6 empty] | 160 |  |  | 8
| Cleaner | Valery | 8 | 15 | Katherine Rojas | Construction Clean | [6 empty] | 120 |  |  | 8
| Cleaner | Anyela | 8 | 15 | Katherine Rojas | Construction Clean | [6 empty] | 120 |  |  | 8
| Cleaner | Oscar | 8 | 20 | Katherine Rojas | Construction Clean | [6 empty] | 160 |  |  | 8
| Cleaner | Anthony | 8 | 16.35 | Katherine Rojas | Construction Clean | [6 empty] | 130.8 |  |  | 8
| Cleaner | Achanti | 8 | 15 | Katherine Rojas | Construction Clean | [6 empty] | 120 |  |  | 8
2026-05-12 | PM | Katherine Rojas | 8 | 20 | Katherine Rojas | Construction Clean | [6 empty] | 160 |  |  | 8
| Cleaner | Valery | 8 | 15 | Katherine Rojas | Construction Clean | [6 empty] | 120 |  |  | 8
| Cleaner | Anyela | 8 | 15 | Katherine Rojas | Construction Clean | [6 empty] | 120 |  |  | 8
| Cleaner | Achanti | 8 | 15 | Katherine Rojas | Construction Clean | [6 empty] | 120 |  |  | 8
| Cleaner | Malbira | 8 | 16.35 | Katherine Rojas | Construction Clean | [6 empty] | 130.8 |  |  | 8
2026-05-13 | PM | Katherine Rojas | 8 | 20 | Katherine Rojas | Construction Clean | [6 empty] | 160 |  |  | 8
| Cleaner | Valery | 8 | 15 | Katherine Rojas | Construction Clean | [6 empty] | 120 |  |  | 8
| Cleaner | Flor | 8 | 15 | Katherine Rojas | Construction Clean | [6 empty] | 120 |  |  | 8
| Cleaner | Anthony | 8 | 16.35 | Katherine Rojas | Construction Clean | [6 empty] | 130.8 |  |  | 8
| Cleaner | Achanti | 8 | 15 | Katherine Rojas | Construction Clean | [6 empty] | 120 |  |  | 8
Brightview, Brick, NJ - 1568 New Jersey 88 - Harkins Builders |  |  |  |  | David Rodriguez | Final Cleaning | 0% |  |  |  |  | 36188
Ardmore House II - Harkins Builders - 55 Ardmore Avenue, Ardmore PA 19003 |  |  |  |  | David Rodriguez | Final Cleaning
Ardmore House II - Harkins Builders - 55 Ardmore Avenue, Ardmore PA 19003 |  |  |  |  | David Rodriguez | Change Order
2026-04-30 | PM | David Rodriguez | 4 | 28.84 | David Rodriguez | Final Cleaning | [6 empty] | 115.36 |  |  | 4
| Cleaner | Oscar Giraldo | 4 | 25 | David Rodriguez | Final Cleaning | [6 empty] | 100 |  |  | 4
| Cleaner | Zakeem Doughty | 4 | 16.35 | David Rodriguez | Final Cleaning | [6 empty] | 65.4 |  |  | 4
| Cleaner | Don Albeiro | 4 | 18 | David Rodriguez | Final Cleaning | [6 empty] | 72 |  |  | 4
2026-05-01 | PM | David Rodriguez | 3.5 | 28.84 | David Rodriguez | Final Cleaning | [6 empty] | 100.94 |  |  | 3.5
| Cleaner | Oscar Giraldo | 3.5 | 25 | David Rodriguez | Final Cleaning | [6 empty] | 87.5 |  |  | 3.5
| Cleaner | Arelis Campaz | 3.5 | 16.35 | David Rodriguez | Final Cleaning | [6 empty] | 57.225 |  |  | 3.5
| Cleaner | Andres Campaz | 3.5 | 15 | David Rodriguez | Final Cleaning | [6 empty] | 52.5 |  |  | 3.5
| Cleaner | Jahbulani Shawn | 3.5 | 20 | David Rodriguez | Final Cleaning | [6 empty] | 70 |  |  | 3.5

## Project Tracking Residential
PROJECT DETAILS | [10 empty] | COST/HOURS |  |  |  |  | Invoicing
DATE | JOB TITLE | NAME | HOURS | RATE/HR | Supervisor | DESCRIPTION | % DONE | CONTRACT VALUE | ESTIMATED MATERIAL COST | ESTIMATED TRAVEL EXPENSE | ESTIMATED LABOR COST | ACTUAL LABOR COST | ACTUAL MATERIAL COST | ESTIMATED HOURS | ACTUAL HOURS | % Invoiced | Invoice Status
683 N Manor Rd, Elverson, PA 19520 - Lynzie Orlandi | [6 empty] | 100% | 3200 |  |  |  | 1374.39 | 400 |  | 55
2026-03-20 | PM | David Rodriguez | 8 | 28.84 | David Rodriguez | Powerwashing Pre-paint | [5 empty] | 230.72 |  |  | 8
| Cleaner | Oscar Giraldo | 8 | 25 | David Rodriguez | Powerwashing Pre-paint | [5 empty] | 200 |  |  | 8
2026-03-23 | PM | David Rodriguez | 2.5 | 28.84 | David Rodriguez | Exterior Painting | [5 empty] | 72.1 |  |  | 2.5
| Cleaner | Oscar Giraldo | 2.5 | 25 | David Rodriguez | Exterior Painting | [5 empty] | 62.5 |  |  | 2.5
| Cleaner | William Sotelo | 2.5 | 18.75 | David Rodriguez | Exterior Painting | [5 empty] | 46.875 |  |  | 2.5
2026-03-26 | PM | David Rodriguez | 10.5 | 28.84 | David Rodriguez | Exterior Painting | [5 empty] | 302.82 |  |  | 10.5
| Cleaner | Oscar Giraldo | 10.5 | 25 | David Rodriguez | Exterior Painting | [5 empty] | 262.5 |  |  | 10.5
| Cleaner | Margarita | 10.5 | 18.75 | David Rodriguez | Exterior Painting | [5 empty] | 196.875 |  |  | 10.5
0%
0%
0%
0%
0%
0%
0%
0%
0%
Paid
Paid
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Turns
PROJECT DETAILS | [10 empty] | Invoicing
DATE | Building | JOB TITLE | LAYOUT | NAME | HOURS | RATE/HR | Supervisor | DESCRIPTION | % DONE | TOTAL | % Invoiced | Invoice Status
UDR (KOP) | [6 empty] | David Rodriguez | Cleaning Turns
2025-08-14 | The Smith (KOP) | Claen unit 4148 | 2025-01-01 | Derly / David | 2.5 | 22.5 | David Rodriguez | Final Clean | 100% | 56.25
2025-08-15 | The Smith (KOP) | Clean unit 4142 | 2025-01-01 | Jhon / David | 2.5 | 30 | David Rodriguez | Final Clean | 100% | 60
2025-08-18 | The Smith (KOP) | Clean unit 3139 | 2025-01-01 | Deivis | 4 | 15 | David Rodriguez | Final Clean | 100% | 60
2025-08-19 | The Smith (KOP) | Clean unit 6121 | 2025-02-02 | Deivis | 3 | 15 | David Rodriguez | Final Clean | 100 | 45
| The Smith (KOP) | Clean unit 6121 | 2025-02-02 | Malbira | 3 | 15 | David Rodriguez | Final Clean | 100% | 45
| The Smith (KOP) | Clean unit 4134 | 2025-01-01 | Deivis | 2.5 | 15 | David Rodriguez | Final Clean | 100% | 37.5
| The Smith (KOP) | Clean unit 4134 | 2025-01-01 | Malbira | 2.5 | 15 | David Rodriguez | Final Clean | 100% | 37.5
| The Smith (KOP) | Clean unit 1140 | 2025-01-01 | Deivis | 2.5 | 15 | David Rodriguez | Final Clean | 100% | 37.5
| The Smith (KOP) | Clean unit 1151 | 2025-01-01 | Malbira | 2.5 | 15 | David Rodriguez | Final Clean | 100% | 37.5
2025-08-20 | The Smith (KOP) | Clean unit 3146 | 2025-02-02 | David | 4 | 27.5 | David Rodriguez | Final Clean | 100% | 110
2025-08-26 | The Smith (KOP) | Clean unit 6153 | 2025-03-02 | Milena | 4.5 | 22.5 | David Rodriguez | Final Clean | 100% | 101.25
2025-08-27 | The Smith (KOP) | Clean unit 1115 | 2025-02-02 | Angela | 4 | 22.5 | David Rodriguez | Final Clean | 100% | 90
2025-08-28 | The Smith (KOP) | Clean unit 1133 | 2025-01-01 | Angela | 3 | 22.5 | David Rodriguez | Final Clean | 100% | 67.5
2025-09-02 | The Smith (KOP) | Clean unit 4115 | 2025-02-02 | Deivis | (4.5) 6.6 | 15 | David Rodriguez | Final Clean | 100% | 100
2025-09-03 | The Smith (KOP) | Clean unit 2126 | 2025-01-01 | Fernanda | 4 | 15 | David Rodriguez | Final Clean | 100% | 60
2025-09-03 | The Smith (KOP) | Clean unit 5144 | 2025-01-01 | Fernanda | 4 | 15 | David Rodriguez | Final Clean | 100% | 60
2025-09-05 | The Smith (KOP) | Clean unit 4103 | 2025-02-02 | Jhon | 4.5 | 30 | David Rodriguez | Final Clean | 100% | 135
2025-12-16 | The Smith (KOP) | Turn unit 2108 | Common Areas | Malbira Pereira | 2 | 15 | David Rodriguez | Final Clean | 100% | 30
| The Smith (KOP) | Turn unit 4108 | Common Areas | Malbira Pereira | 2 | 15 | David Rodriguez | Final Clean | 100% | 30
2025-12-19 | The Smith (KOP) | Turn unit 5108 | Common Areas | Diana Diaz | 2 | 15 | David Rodriguez | Final Clean | 100% | 30
| The Smith (KOP) | Turn unit 3108 | Common Areas | Diana Diaz | 2 | 15 | David Rodriguez | Final Clean | 100% | 30
2026 | 2026 | 2026 | 2026 | 2026 | 2026 |  | 2026 | 2026
2026-02-06 | Park Square | Clean 12 chute | Chute gates | Oscar | 6.5 | 25 | David Rodriguez | Clean chute gates | 100% | 162.5
2026-03-10 | Park Square | Clean exterior windows lobbies | 4 lobbies, one in each building | Oscar | 8 | 25 | David Rodriguez | Clean exterior windows | 100% | 200
THE GIO | [6 empty] | David Rodriguez | Cleaning & Painting Turns |  |  | 100% | Billing
02/29/26 | The Gio | Clean unit 9084 | 2026-01-01 | Oscar Giraldo | 4 | 25 | David Rodriguez | Deep Clean | 100% | 100
2026-03-03 | The Gio | Paint unit 308 | 2026-02-02 | Oscar Giraldo | 8 | 25 | David Rodriguez | Full Paint | 100% | 200
|  |  |  | Elian Bonilla | 8 | 18.75 | David Rodriguez | Full Paint | 100% | 150 | 350
2026-03-05 | The Gio | Clean unit 402 | 2026-01-01 | Oscar Giraldo | 3 | 25 | David Rodriguez | Deep Clean | 100% | 75
|  |  |  | Elian Bonilla | 3 | 15 | David Rodriguez | Deep Clean | 100% | 45
| The Gio | Clean unit 9077 | 2026-02-02 | Oscar Giraldo | 5 | 25 | David Rodriguez | Deep Clean | 100% | 125
|  |  |  | Elian Bonilla | 5 | 15 | David Rodriguez | Deep Clean | 100% | 75 | 320
| The Gio | 308 unit repairs |  | David Rodriguez | 8 | 28.84 | David Rodriguez | Tapes Corners Repair | 100% | 230.72
2026-03-06 | The Gio | Clean Unit 308 | 2026-02-02 | Oscar Giraldo | 3.5 | 25 | David Rodriguez | Deep Clean | 100% | 87.5
2026-03-09 | The Gio | Clean unit 9017 | 2026-02-02 | Oscar Giraldo | 3 | 25 | David Rodriguez | Deep Clean | 100% | 75
2026-04-01 | The Gio | Clean unit 9011 | 2026-01-01 | David Rodriguez | 9 | 28.84 | David Rodriguez | Paint / Clean | 100% | 259.56
|  |  |  | Oscar Giraldo | 9 | 25 | David Rodriguez | Paint / Clean | 100% | 225 | 484.56
2026-04-06 | The Gio | Guarantee unit 9011 | 2026-01-01 | David Rodriguez | 3 | 28.84 | David Rodriguez | Paint / Clean | 100% | 86.52 | 86.52 | 500 paint | 150 clean
2026-04-08 | The Gio | Unit 407 | 2026-01-01 | David Rodriguez | 5.5 | 28.84 | David Rodriguez | Paint / Clean | 100% | 158.62
THE BLOCK AT SONO | [6 empty] | David Rodriguez | Cleaning & Painting Turns |  |  | 100% | Billing
2026-02-05 | SONO | Clean unit # 7 | 2026-01-01 | Oscar | 4 | 25 | David Rodriguez | Dep Clean | 100% | 100
|  | Clean unit # 21 | 2026-02-02 | Oscar | 4.5 | 25 | David Rodriguez | Dep Clean | 100% | 112.5 | 212.5
2026-05-05 | SONO | Paint unit # 10 A | 2026-01-01 | Oscar Giraldo | 4 | 25 | Oscar Giraldo | Touch up Paint | 100% |  |  | 500
|  |  |  | William Sotelo | 4 | 16.35 |  | Touch up Paint | 100%
|  | Paint unit # 10 B | 2026-01-01 | Oscar Giraldo | 3.5 | 25 | Oscar Giraldo | Touch up Paint | 100% |  |  | 500
|  |  |  | William Sotelo | 3.5 | 16.35 |  | Touch up Paint | 100%
|  | Paint unit # 6 | 2026-01-01 | Oscar Giraldo | 3.5 | 25 | Oscar Giraldo | Touch up Paint | 100% |  |  | 500
|  |  |  | William Sotelo | 3.5 | 16.35 |  | Touch up Paint | 100%
2026-05-06 | SONO | Cleaning unit # 10A | 2026-01-01 | Katherin Rojas | 2.5 | 20 | Katherin Rojas | Cleaning |  |  |  | 150
|  |  |  | Dayonna Lewis | 1 | 16.35 |  | Cleaning
|  | Cleaning unit # 10B | 2026-01-01 | Katherin Rojas | 3 | 20 | Katherin Rojas | Cleaning |  |  |  | 150
|  |  |  | Dayonna Lewis | 2.5 | 16.35 |  | Cleaning
|  | Cleaning unit # 6 | 2026-01-01 | Katherin Rojas | 2.5 | 20 | Katherin Rojas | Cleaning |  |  |  | 150
|  |  |  | Dayonna Lewis | 2.5 | 16.35
2026-05-06 | SONO | Guarantee unit # 6 | 2026-01-01 | Katherin Rojas | 5 | 20 | Katherin Rojas | Paint / Clean
|  |  |  | Zakeem Doughty | 4 | 20 |  | Paint / Clean
Vermella East & Vermella West - Russo Management | [6 empty] | David Rodriguez | Cleaning & Painting Turns |  |  | 100% | Billing
2026-04-10 | Vermella East | Unit 202 Building 64 | 2026-02-02 | David Rodriguez | 7 | 28.84 | David Rodriguez | Paint / Clean | 100% | 201.88
|  |  |  | Oscar Giraldo | 7 | 25 |  |  |  | 175
|  |  |  | Angela | 7 | 15 |  |  |  | 105
|  |  |  | Arelis | 7 | 15 |  |  |  | 105
586.88
2026-04-15 | Vermella East | Touch upUnit 202 Building 64 | 2026-02-02 | David Rodriguez | 4 | 28.84 | David Rodriguez | Guarantee | 100% | 115.36
|  |  |  | Franklin Olivares | 4 | 20 |  |  |  | 80
195.36
Chesnut Hall Apartnents | [6 empty] | David Rodriguez | Cleaning & Painting Turns |  |  | 100% | Billing
2026-05-12 | Chesnut Hall | Unit 904 | 2026-01-01 | Oscar Giraldo | 9 | 25 | Oscar Giraldo | Full Paint | 100% | 225
|  |  |  | Flor Isaguirre | 9 | 15 |  | Cleaning | 100% | 135 | 360

## Worker Verification
WORKER VERIFICATION
Worker Name | Job Title | Hourly Pay | Project | Verified ID | Background Check | OSHA Cert | Start Date | Phone number | Email
Jhon Fonseca | Manager | 20 | UDR | approved |  |  | 2026-01-19 | 857-764-3718 | jfonseca.devisab@gmail.com
Maria Hormaza | Cleaner | 16.35 | UDR | incomplete |  |  | 2026-01-16 | 929-374-9683 | mafe.9@hotmail.com
Sandra Camacho | Cleaner | 16.35 | UDR | Pending |  |  | 2026-01-19 | 267-243-9784 | smilenacamacho5522@gmail.com
Derly Garzon | Cleaner | 16.35 | UDR | approved |  |  | 2026-01-19 | 267-243-9784 | demagaro@hotmail.com
Ferney Pineda | Cleaner | 16.35 | UDR | approved |  |  | 2026-01-19 | 267-439-1698 | ferney.solano0808@gmail.com
Angela Calderon | Cleaner | 18.75 | UDR | approved |  |  | 2026-01-19 | 215-758-4967 | calderongarcia0915@gmail.com
James Fowler | Cleaner | 18.75 | UDR | approved |  |  | 2026-01-19 | 215-917-6748 | edwinguevararojas1978@gmail.com
Oscar Giraldo | Manager | 25 | saddlebrook |  |  |  | 2018-03-16 | 267-592-9334 | oagh0822@gmail.com
Elian Bonilla | painter/cleaner | 15 | saddlebrook | not completed |  |  |  | Not registered in ADP
Malbira Pereira | painter/cleaner | 15 | saddlebrook | not completed |  |  |  | 929-723-0557 | malbirapereira@gmail.com
David Rodriguez | [5 empty] | Osha 30
Oscar Giraldo
Bastian Sepulveda | superintendent | 20 | [5 empty] | 293-99-1559 | 239-99-1559 | sepulvedabarriosbastian@gmail.com
Jhon Jairo Foonseca Pinzon | UDR Cleaner | 20 | [5 empty] | 135-39-5386 | 845-764-3718 | jfonseca.devisab@gmail.com
Lina Maria Acevedo Ramirez | UDR Cleaner | 15 | [5 empty] | 942-99-2264 ITIN | 203-609-5583 | linisramirez5@gmail.com
Maria Fernanda Hormaza Giraldo | UDR Cleaner | 16.35 |  |  |  |  | 2026-01-15 | 762-48-3812 | 929-374-9683 | mafe.9@hotmail.com
Sandra Milena Camacho Parra | UDR Cleaner | 15 | [5 empty] | 856-03-0095 | 267-243-9784 | smilenacamacho5522@gmail.com
Derly Margarita Garzon | UDR Cleaner | 15 | [5 empty] | 359-25-8745 |  | demagaro@hotmail.com
Ferney Solano Pineda | UDR Cleaner | 15 | [5 empty] | 837-36-5922 | 267-439-1698 | ferney.solano0808@gmail.com
Angela Maria Calderon Garcia | UDR Cleaner | 18.75 | [5 empty] | 654-96-9050 | 215- 758- 4967 | calderongarcia0915@gmail.com
Victor Manuel Tzun Lopez | UDR Cleaner | 18.75 | [5 empty] | 631-81-9523 | 743-249-6563 | tzunlopezvictor@gmail.com
Edwin Guevara Rojas | UDR Cleaner | 18.75 | [5 empty] | 236-61-9171 | 215-917-6748 | edwinguevararojas1978@gmail.com
Franklin Adan Coy Bo | Painter | 18.75 | [5 empty] | 485-75-9136 | 267-541-5162 | coybofranklina@gmail.com
Yuly Selena Chaverra Molano | Painter | 18.75 | [5 empty] | 091-15-5776 | 862-296-3745 | yscm2002m@gmail.com
Carlos Rene Hernandez Pacheco | Painter | 18.75 | [5 empty] | 920-97-3761 | 609-478-9516 | charlih622@gmail.com
Mayra Juditch de Paz Ramos de Hernandez | Painter | 18.75 | [6 empty] | 267-918-2305 | daniel.-123456@hotmail.com
Jaime Daniel Paucar Gomez | Painter | 18.75 | [6 empty] | 653-03-9231
Oscar Hernandez | Painter | 18.75 |  |  |  |  | 2025-11-20 | 975-95-3423 ITIN | 267-980-7049 | oscar.hernandez.e@icloud.com
2025-11-18
Diana Diaz | Cleaner | 15 | Luisa Pinto |  |  |  |  | 209-82-9124 | 445-207-0386 | dianadiazriveros@icloud.com
Camila Cardenas | Cleaner | 15 | Luisa Pinto |  |  |  |  | 209-82-9124 | 267-632-8564 | mcardenasdiaz@icloud.com
Malbira Pereira | Cleaner | 15 | [5 empty] | 676-33-4693 | 929-723-0557 | malbirapereira@gmail.com
Elian Bonilla | Cleaner | 18.75 | Yuly Chaverra